## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Jhargram Mechanical Division | Solarization of grid connected pumping installation Kashijora PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17798 | Solarisation | Quotation bill for Providing solarization of WBSEDCL energised pumping installation at Kashijora w/s scheme (T/W No. I) |  |  | BILL/00578/2024-2025 | 257/JMD | 10/07/2024 | 10/07/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Jhargram Mechanical Division | Solarization of grid connected pumping installation Kashijora PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17798 | Solarisation | Quation bill for Kashijora T/W -I PWSS |  |  | BILL/01359/2024-2025 | 425/JMD | 27/11/2024 | 27/11/2024 | WBSEDCL | 0.23 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation Kashijora PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17798 | Solarisation | Solarization of grid connected pumping installation Kashijora PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002048/2022-2023 | 967/W/MMD | 29/03/2023 | 18/03/2025 | RSA ENTERPRISE | 6.25 | 0 | 0 | 100
Total | [13 empty] | 6.48 | 0 | 0