## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation Mansuka PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17799 | Solarisation | Solarization of grid connected pumping installation Mansuka PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002087/2022-2023 | 992/W/MMD | 29/03/2023 | 25/09/2023 | ABHIJIT MUKHERJEE | 6.25 | 4.88 | 78.03 | 77
2 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation Mansuka PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17799 | Solarisation | Supply and installation of sign board for depicting the scheme details of different on-going solarisation / rejuvenation as per Annexure-B under JJM works for the purpose of Geotagging under Midnapore Mechanical Division, P.H.E. Dte. Dist. - Paschim Medinipur. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000013/2024-2025 | 715/MMSD-I | 07/06/2024 | 22/06/2024 | MUKHERJEE ART CENTRE | 1.93 | 0.19 | 10 | 100
Total | [13 empty] | 8.18 | 5.07 | 61.95