## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Suktajuri PWSS in the District of Paschim Medinipur under JJM programme. | SM/17820 | Augmentation | Electric quotation for Load enhancement at Tw no-I of Suktajuri water supply scheme. Consumer ID-200331905. |  |  | BILL/00268/2023-2024 | null | 22/05/2023 |  | WBSEDCL | 0.36 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Suktajuri PWSS in the District of Paschim Medinipur under JJM programme. | SM/17820 | Augmentation | Rejuvenation of Electro-Mechanical components of Suktajuri PWSS in the District of Paschim Medinipur under JJM programme under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002126/2022-2023 | 1064/W/MMD | 29/03/2023 | 25/09/2023 | TAPAN KUMAR SARKAR | 21.01 | 0 | 0 | 52
Total | [13 empty] | 21.38 | 0 | 0