## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Panskura,Pingla | Midnapore Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PINGLA,KHARAGPUR-II & PANSKURA BLOCK,DISTRICT - PASCHIM & PURBA MEDINIPUR (PHASE-I) | SM/19188 | New | Construction of 11/0.433 KV, 800 KVA Electrical Substation with allied Electrical works at Pingla Boosting at panskura under surface water based water supply scheme for Pingla, Panskura and Khargpur-II Block in Purba & Paschim Medinipur District under JJM under Midnapore Mechanical Division, PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division | ORD/002705/2023-2024 | 1057/W/MMD | 13/03/2024 | 09/09/2024 | APEX ENGINEERING & PROJECT CO | 338.92 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Panskura,Pingla | Midnapore Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PINGLA,KHARAGPUR-II & PANSKURA BLOCK,DISTRICT - PASCHIM & PURBA MEDINIPUR (PHASE-I) | SM/19188 | New | Construction of 11/0.433 KV, 1600 KVA Electrical Substation with allied Electrical works at Intake point (River bank) at panskura under surface water based water supply scheme for Pingla, Panskura and Khargpur-II Block in Purba & Paschim Medinipur District under JJM under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri, Bikas Pramanik, JE, Estimator MMD | ORD/002717/2023-2024 | 1058/W/MMD | 13/03/2024 | 09/09/2024 | THE MARKET ELECTRICAL ENGINEERING WORKS | 485.76 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Panskura,Pingla | Midnapore Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PINGLA,KHARAGPUR-II & PANSKURA BLOCK,DISTRICT - PASCHIM & PURBA MEDINIPUR (PHASE-I) | SM/19188 | New | Material Requisition To Resource Division |  |  | RTOR000002/2024-2025 | 2240/MD | 22/07/2024 | 22/07/2024 | Resource Division | 237.7 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Panskura,Pingla | Midnapore Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PINGLA,KHARAGPUR-II & PANSKURA BLOCK,DISTRICT - PASCHIM & PURBA MEDINIPUR (PHASE-I) | SM/19188 | New | Construction of 33/0.433 KV, 3000 KVA Electrical Substation with allied Electrical works at WTP at Panskura under surface water based water supply scheme for Pingla, Panskura and Khargpur-II Block in Purba & Paschim Medinipur District under JJM under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000163/2024-2025 | 1659/W/MMD | 29/07/2024 | 25/01/2025 | THE MARKET ELECTRICAL ENGINEERING WORKS | 747.99 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Panskura,Pingla | Midnapore Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PINGLA,KHARAGPUR-II & PANSKURA BLOCK,DISTRICT - PASCHIM & PURBA MEDINIPUR (PHASE-I) | SM/19188 | New | Supplying, laying of 9 nos zone Distribution System including specials, valves & pipe carrying structure, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule (dept. supply), saddle piece etc. all complete, Construction of 9 Nos. various capacities of 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials., Soil Investigation for the work of construction of OHR, Construction of Switch room cum Chlorine Room Including Chlorination &Sanitary Arrangement, Boundary Wall, Service Road for 50 M length, Improvement of Land for each site, Renovation of 4 nos. Existing OHRs. surface Drain, Campus lighting & other provisional works etc for Pingla Block on EPC turnkey basis in a single package as per detail scope of work / direction of the E-I-C including 6(six) months Trial Run and Operation& Maintenance for 5(five) years for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME for Pingla, Panskura Block, District Paschim & Purba Medinipur under Western Circle, PHE Dte. (Phase-I) | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla),JE1 Kharagpur Sub-division | ORD/000837/2023-2024 | 801/MD | 15/03/2024 | 16/09/2026 | G B CONSTRUCTION & UMWELT JV | 7243.56 | 0 | 0 | 10
6 | PURBA MEDINIPUR | Panskura,Pingla | Tamluk Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PINGLA,KHARAGPUR-II & PANSKURA BLOCK,DISTRICT - PASCHIM & PURBA MEDINIPUR (PHASE-I) | SM/19188 | New | Surveying, Designing, Engineering, Supplying, Construction, Erectioning, Testing, Commissioning of Raw Water Intake Jetty Structure (Fixed type) with Pump House connected by RCC carriageway with the river bank, 70 MLD capacity conventional type Water Treatment Plant, Raw Water Rising Mains, Bank protection, Substation Building for Intake and WTP, Clear Water Reservoir, High Lift Pump House, Clear Water Rising Mains, 1000 Cum capacity UGR cum Booster Pumping Station at Pingla block , Chlorine room & Guard room at UGR site with necessary sanitary arrangements including plinth protection work with surface drain, Administrative Building with centralized SCADA system, Bunglow & Staff Quarter including furniture at WTP & other necessary all Civil and Electro-Mechanical works [excluding substation equipments] etc on EPC turnkey basis as per direction of the EIC including 6(six) months Trial Run and Operation & Maintenance for 5(five) years for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME for Pingla, Panskura Block, District Purba & Paschim Medinipur (Phase-I) | Assistant Engineer |  | ORD/001219/2023-2024 | 1012/TD | 14/03/2024 | 14/03/2026 | G. B. CONSTRUCTION | 28900 | 0 | 0 | 12
7 | PURBA MEDINIPUR | Panskura,Pingla | Tamluk Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PINGLA,KHARAGPUR-II & PANSKURA BLOCK,DISTRICT - PASCHIM & PURBA MEDINIPUR (PHASE-I) | SM/19188 | New | Supplying, laying of 22 nos zone Distribution System including specials, valves & pipe carrying structure, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule (dept. supply), saddle piece etc. all complete, Construction of 25 Nos. various capacities of 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials., Soil Investigation for the work of construction of OHR, Construction of Switch room cum Chlorine Room Including Chlorination & Sanitary Arrangement, Boundary Wall, Service Road for 50 M length & Improvement of Land for each site, surface Drain, Campus lighting & other provisional works etc for Panskura Block on EPC turnkey basis in a single package as per detail scope of work / direction of the E-I-C including 6(six) months Trial Run and Operation & Maintenance for 5(five) years for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME for Panskura Block, District Paschim & Purba Medinipur under Western Circle, PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer | ORD/000183/2024-2025 | 2258/TD | 16/07/2024 | 16/07/2029 | M/S ANAND SINGH | 18090.51 | 0 | 0 | 5
Total | [13 empty] | 56044.45 | 0 | 0