## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Chandipur | Tamluk Division | Newly setup Digha Sub-Divisional Laboratory within the Compound of Headwork Site of Digha Augmentation W/S Scheme (Eastern Zone) under Digha Sub-Division of Tamluk Division, PHE Dte. | SM/06651 | New | Different work under Tamluk Division, PHE Dte. |  |  | VCH/000165/2020-2021 | 05 | 16/04/2020 | 16/04/2020 | DIFFERENT CONTRACTOR OF TAMLUK DIVISION, PHE DTE. | 9.82 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Chandipur | Tamluk Division | Newly setup Digha Sub-Divisional Laboratory within the Compound of Headwork Site of Digha Augmentation W/S Scheme (Eastern Zone) under Digha Sub-Division of Tamluk Division, PHE Dte. | SM/06651 | New | Different work under Tamluk Division, PHE Dte. |  |  | VCH/000166/2020-2021 | 06 | 16/04/2020 | 16/04/2020 | DIFFERENT CONTRACTOR OF TAMLUK DIVISION, PHE DTE. | 8.25 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Chandipur | Tamluk Division | Newly setup Digha Sub-Divisional Laboratory within the Compound of Headwork Site of Digha Augmentation W/S Scheme (Eastern Zone) under Digha Sub-Division of Tamluk Division, PHE Dte. | SM/06651 | New | Annual Maintenance of Computer and Peripherals for different laboratories in Purba Medinipur District under Tamluk Division, PHE Dte. (Period from 01/11/20 to 28/02/2021) |  |  | VCH/000074/2021-2022 | 08/W | 05/05/2021 | 05/05/2021 | MISHRA ENTERPRISE | 0.78 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Chandipur | Tamluk Division | Newly setup Digha Sub-Divisional Laboratory within the Compound of Headwork Site of Digha Augmentation W/S Scheme (Eastern Zone) under Digha Sub-Division of Tamluk Division, PHE Dte. | SM/06651 | New | Contigency Bill of NGO managed laboratory for the period from October, 2020 to March, 2021. under Tamluk Division, PHE Dte. |  |  | VCH/000215/2021-2022 | 161/W | 30/07/2021 | 30/07/2021 | TAMRALIPTA GUCHHA SAMITY AND OTHERS | 2.45 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Chandipur | Tamluk Division | Newly setup Digha Sub-Divisional Laboratory within the Compound of Headwork Site of Digha Augmentation W/S Scheme (Eastern Zone) under Digha Sub-Division of Tamluk Division, PHE Dte. | SM/06651 | New | Instrument / Equipment for Digha Sub-Divisional Water Testing Laboratory under Digha Sub-Division of Tamluk Division, PHE Dte. |  |  | VCH/001059/2020-2021 | 1115/W | 30/03/2021 | 30/03/2021 | LABARD INSTRUCHEM PVT. LTD. | 8.06 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Chandipur | Tamluk Division | Newly setup Digha Sub-Divisional Laboratory within the Compound of Headwork Site of Digha Augmentation W/S Scheme (Eastern Zone) under Digha Sub-Division of Tamluk Division, PHE Dte. | SM/06651 | New | THIS BILL HAS BEEN RAISED FOR SURRENDER OF UNSPENT FUND TO THE SINGLE NODAL ACCOUNT AS PER CLAUSE 2(III) OF D.O. NO. F.1(13)PFMS/FCD/2020, DTD. 12TH APRIL, 2021 BY SECRETARY, EXPENDITURE, GOVT. OF INDIA, MINISTRY OF FINANCE, DEPARTMENT OF EXPENDITURE AND CLAUSE 13 OF OFFICE MEMORANDUM. NO. F.I. (13) PFMS FCD / 2020 DTD. 23/03/2021 BY THE DIRECTOR (FCD), GOVT. OF INDIA, MINISTRY OF FINANCE, DEPARTMENT OF EXPENDITURE, PFMS DIVISION, AND VIDE MEMO NO. 2724/PHE-13011/7/2021-BUDGET CELL-DEPT. OF PHE Dte. |  |  | VCH/000706/2021-2022 | 452/W | 22/12/2021 | 22/12/2021 | JAL JEEVAN MISSION WEST BENGAL ESCROW ACCOUNT | 7.13 | 0 | 0 | 0
Total | [13 empty] | 36.49 | 0 | 0