## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Barasubarnanagar W/S Scheme | SM/06877 | Retrofitting | Retrofitting to accommodate FHTC under JJM within Barasubarnanagar PWSS Block Contai-II in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000031/2020-2021 | 2107/TD | 05/11/2020 | 04/05/2021 | PRANAB KUMAR DAS | 96.08 | 31.17 | 32.44 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Barasubarnanagar W/S Scheme | SM/06877 | Retrofitting | Retrofitting to accomodate FHTC under JJM Bara Subarnagar W/S Scheme within Deshapran Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001254/2020-2021 | 992/W | 27/03/2021 | 27/03/2021 | PRANAB KUMAR DAS | 56.48 | 0 | 0 | 0
Total | [13 empty] | 152.56 | 31.17 | 20.43