## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Bamunia W/S Scheme | SM/06878 | Retrofitting | Retrofitting to accommodate FHTC under JJM within Bamunia PWSS Block Contai-II in the District of Purba Medinipur. | Assistant Engineer |  | ORD/000030/2020-2021 | 2106/TD | 05/11/2020 | 04/05/2021 | JAYANTA KR. MONDAL | 74.72 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Bamunia W/S Scheme | SM/06878 | Retrofitting | Retrofitting to accomodate FHTC under JJM Bamunia W/S Scheme within Contai - II Block under Tamluk Division, PHE Dte. |  |  | VCH/000601/2020-2021 | 639/W | 13/01/2021 | 13/01/2021 | JAYANTA KUMAR MONDAL | 54.64 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Bamunia W/S Scheme | SM/06878 | Retrofitting | Retrofitting to accomodate FHTC under JJM Bamunia W/S Scheme within Contai - II Block under Tamluk Division, PHE Dte. |  |  | VCH/001242/2020-2021 | 995/W | 26/03/2021 | 26/03/2021 | JAYANTA KUMAR MONDAL | 10.33 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Bamunia W/S Scheme | SM/06878 | Retrofitting | Retrofitting to accomodate FHTC under JJM Bamunia W/S Scheme within Contai - II Block under Tamluk Division, PHE Dte. |  |  | VCH/000430/2021-2022 | 303/W | 05/10/2021 | 05/10/2021 | JAYANTA KUMAR MONDAL | 5 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Bamunia W/S Scheme | SM/06878 | Retrofitting | Retrofitting to accomodate FHTC under JJM Bamunia W/S Scheme within Contai - II Block under Tamluk Division, PHE Dte. |  |  | VCH/000374/2021-2022 | BP-2021-22-121 | 05/10/2021 | 05/10/2021 | JAYANTA KUMAR MONDAL | 3.99 | 0 | 0 | 0
Total | [13 empty] | 148.68 | 0 | 0