## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Bankiput W/S Scheme | SM/06879 | Retrofitting | Functional Household Tap Connection to the 311 nos. Household of Bankiput Water Supply Scheme within Contai-II (Deshapran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. i) Payrakola (609) ii) Bargolia (610) iii) Hajrakola (611) iv) Bhogpur (624) v) Kalichar (626) vi) Kalidasbar (627). | Assistant Engineer |  | ORD/000095/2020-2021 | 2451/TD | 18/12/2020 | 07/01/2021 | AHINDRA BARIK | 15.31 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Bankiput W/S Scheme | SM/06879 | Retrofitting | Functional Household Tap Connection to the 232 nos. Household of Bankiput Water Supply Scheme within Contai-II (Deshapran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. i) Bankipur(629) ii ) Tiakola (630). | Assistant Engineer |  | ORD/000096/2020-2021 | 2452/TD | 18/12/2020 | 07/01/2021 | JASODA ENTERPRISE | 11.46 | 0 | 0 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Bankiput W/S Scheme | SM/06879 | Retrofitting | Functional Household Tap Connection to the 202 nos. Household of Bankiput Water Supply Scheme within Contai-II (Deshapran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. i) Bhupatichak (628) ii ) Kaluraybar (631) iii) Kanaichatta (632). | Assistant Engineer |  | ORD/000097/2020-2021 | 2453/TD | 18/12/2020 | 07/01/2021 | SUBHENDU HAZRA | 10 | 0 | 0 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Bankiput W/S Scheme | SM/06879 | Retrofitting | Retrofitting to accomodate for 275 Nos. FHTC connection under JJM in Bankiput W/S Scheme within Contai - I Dev. Block Block under Tamluk Division, PHE Dte. |  |  | VCH/001049/2020-2021 | 802/W | 24/02/2021 | 24/02/2021 | SUBHENDU HAZRA | 9.68 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Bankiput W/S Scheme | SM/06879 | Retrofitting | Retrofitting to accomodate for 232 Nos. FHTC connection under JJM in Bankiput W/S Scheme within Contai - II Dev. Block Block under Tamluk Division, PHE Dte. |  |  | VCH/001044/2020-2021 | 729/W | 18/02/2021 | 18/02/2021 | JASODA ENTERPRISE | 11.46 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Bankiput W/S Scheme | SM/06879 | Retrofitting | Retrofitting to accomodate for 311 Nos. FHTC connection under JJM in Bankiput W/S Scheme within Contai - II Dev. Block Block under Tamluk Division, PHE Dte. |  |  | VCH/001200/2020-2021 | 861/W | 16/03/2021 | 16/03/2021 | AHINDRA BARIK | 15.01 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Bankiput W/S Scheme | SM/06879 | Retrofitting | Retrofitting to accommodate FHTC 19 Nos. at different School under JJM in Bankiput PWSS Block-Contai - I under Tamluk Division, PHE Dte. |  |  | VCH/000868/2021-2022 | 603/W | 24/02/2022 | 24/02/2022 | JASODA ENTERPRISE | 0.85 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Bankiput W/S Scheme | SM/06879 | Retrofitting | Retrofitting to accommodate FHTC 19 Nos. at different School under JJM in Bankiput PWSS Block-Contai - I under Tamluk Division, PHE Dte. |  |  | VCH/000818/2021-2022 | BP-2021-22-279 | 25/02/2022 | 25/02/2022 | JASODA ENTERPRISE | 0.66 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Bankiput W/S Scheme | SM/06879 | Retrofitting | Laying of 100 mm dia DI(K9) Rising Main pipe line with CIDF pipe & specials at 1(One) no. Boosting Tube Well of Source Augmentation of Bankiput & its adjoining mouzas Water Supply Scheme within Contai-II(Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer |  | ORD/000369/2023-2024 | 1000/TD | 05/06/2023 | 05/07/2023 | GITA ENTERPRISE | 3.39 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Bankiput W/S Scheme | SM/06879 | Retrofitting | Construction of 3.60 mtr. x 3.00 mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Boosting Tube Well of Source Augmentation of Bankiput W/S Scheme within Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division,PHE Dte. | Assistant Engineer |  | ORD/000355/2023-2024 | 1001/TD | 05/06/2023 | 04/08/2023 | GITA ENTERPRISE | 3.97 | 0 | 0 | 0
Total | [13 empty] | 81.78 | 0 | 0