## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Dariapur W/S Scheme | SM/06880 | Retrofitting | Retrofitting to accommodate FHTC under JJM within Dariapur PWSS Block Contai-II in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000032/2020-2021 | 2108/TD | 05/11/2020 | 04/05/2021 | RAJ KUMAR SINGHA | 79.23 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Dariapur W/S Scheme | SM/06880 | Retrofitting | Retrofitting to accomodate FHTC under JJM Dariapur W/S Scheme within Conai - II Block under Tamluk Division, PHE Dte. |  |  | VCH/000599/2020-2021 | 636/W | 13/01/2021 | 13/01/2021 | RAJ KUMAR SINGHA | 76.24 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Dariapur W/S Scheme | SM/06880 | Retrofitting | Land Development at Head Work Site of Dariapur PWSS within Desopran Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000643/2023-2024 | 1584/CSD | 16/08/2023 | 31/08/2023 | JASODA ENTERPRISE | 0.53 | 0 | 0 | 100
Total | [13 empty] | 156 | 0 | 0