## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Amtalia W/S Scheme | SM/06881 | Retrofitting | Retrofitting to accommodate FHTC under JJM within Amtalia PWSS Block Contai-II in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000028/2020-2021 | 2104/TD | 05/11/2020 | 04/05/2021 | ARABINDA GHOSH | 96.58 | 40.55 | 41.99 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Amtalia W/S Scheme | SM/06881 | Retrofitting | Retrofitting to accomodate FHTC under JJM Amtalia W/S Scheme within Conai - II Block under Tamluk Division, PHE Dte. |  |  | VCH/000591/2020-2021 | 635/W | 13/01/2021 | 13/01/2021 | ARABINDA GHOSH | 54.93 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Amtalia W/S Scheme | SM/06881 | Retrofitting | Providing FHTC with allied works of Aladarput and its adjoining mouzas water supply scheme under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer |  | ORD/000748/2022-2023 | 1109 / CSD | 23/12/2022 | 22/01/2023 | MRINAL KANTI PRADHAN | 2.85 | 0 | 0 | 90
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Amtalia W/S Scheme | SM/06881 | Retrofitting | Instalation of display Board at different work site of Amtalia PWSS (Retrofitting) in Deshpran Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer |  | ORD/001189/2023-2024 | 2337/CSD | 29/12/2023 | 05/01/2024 | AMIT PAYRA | 0.21 | 0.21 | 100 | 100
Total | [13 empty] | 154.57 | 40.76 | 26.37