## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Aladarput W/S Scheme | SM/06882 | Retrofitting | Retrofitting to accommodate FHTC under JJM within Aladarput PWSS Block Contai-II in the District of Purba Medinipur. | Assistant Engineer |  | ORD/000029/2020-2021 | 2105/TD | 05/11/2020 | 04/05/2021 | TARUN KOLEY | 96.5 | 188.57 | 195.4 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Aladarput W/S Scheme | SM/06882 | Retrofitting | Providing FHTC with allied works of Aladarput and its adjoining mouzas water supply scheme under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer |  | ORD/000748/2022-2023 | 1109 / CSD | 23/12/2022 | 22/01/2023 | MRINAL KANTI PRADHAN | 2.85 | 0 | 0 | 90
Total | [13 empty] | 99.35 | 188.57 | 189.79