## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Barchunfali W/S Scheme | SM/06883 | Retrofitting | Retrofitting to accommodate FHTC under JJM within Barchunfali PWSS Block Contai-I in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000026/2020-2021 | 2102/TD | 05/11/2020 | 04/05/2021 | DAS CONSTRUCTION | 96.5 | 1.82 | 1.89 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Barchunfali W/S Scheme | SM/06883 | Retrofitting | Retrofitting to accomodate FHTC under JJM of Barchunfali W/S Scheme within Contai - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000612/2020-2021 | 686/W | 27/01/2021 | 27/01/2021 | DAS CONSTRUCTION | 59.4 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Barchunfali W/S Scheme | SM/06883 | Retrofitting | Retrofitting to accomodate FHTC under JJM of Barchunfali W/S Scheme within Contai - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001266/2020-2021 | 1040/W | 30/03/2021 | 30/03/2021 | DAS CONSTRUCTION | 18.19 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Barchunfali W/S Scheme | SM/06883 | Retrofitting | Retrofitting to accomodate FHTC under JJM of Barchunfali W/S Scheme within Contai - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000466/2021-2022 | 311/W | 08/10/2021 | 08/10/2021 | DAS CONSTRUCTION | 16.22 | 0 | 0 | 0
Total | [13 empty] | 190.31 | 1.82 | 0.96