## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Damudarpur W/S Scheme | SM/06884 | Retrofitting | Functional Household Tap Connection to the 275 nos. Household of Damudarpur Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. i) Damudarpur (357) ii) Hamirpur (545). | Assistant Engineer | Junior Engineer | ORD/000098/2020-2021 | 2454/TD | 18/12/2020 | 07/01/2021 | ABHIJIT BERA | 13.49 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Damudarpur W/S Scheme | SM/06884 | Retrofitting | Functional Household Tap Connection to the 237 nos. Household of Damudarpur Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. i) Chandanpur (422) ii) Dakshin Rampur ( 539). | Assistant Engineer | Junior Engineer | ORD/000099/2020-2021 | 2455/TD | 18/12/2020 | 07/01/2021 | PARIA ENTERPRISE | 11.6 | 0 | 0 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Damudarpur W/S Scheme | SM/06884 | Retrofitting | Functional Household Tap Connection to the 233 nos. Household of Damudarpur Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. i) Baliapur (358) ii) Jamna Madhusudhanbar (365). | Assistant Engineer | Junior Engineer | ORD/000100/2020-2021 | 2456/TD | 18/12/2020 | 07/01/2021 | BADAL CHANDRA GOLE | 11.46 | 0 | 0 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Damudarpur W/S Scheme | SM/06884 | Retrofitting | Retrofitting to accomodate for 233 Nos. FHTC connection under JJM in Damudarpur W/S Scheme within Contai - I Dev. Block Block under Tamluk Division, PHE Dte. |  |  | VCH/001214/2020-2021 | 956/W | 19/03/2021 | 19/03/2021 | BADAL CHANDRA GOLE | 10.24 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Damudarpur W/S Scheme | SM/06884 | Retrofitting | Retrofitting to accomodate for 233 Nos. FHTC connection under JJM in Damudarpur W/S Scheme within Contai - I Dev. Block Block under Tamluk Division, PHE Dte. |  |  | VCH/000475/2021-2022 | 325/W | 08/10/2021 | 08/10/2021 | BADAL CHANDRA GOLE | 0.81 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Damudarpur W/S Scheme | SM/06884 | Retrofitting | Retrofitting to accomodate for 275 Nos. FHTC connection under JJM in Damudarpur W/S Scheme within Contai - I Dev. Block Block under Tamluk Division, PHE Dte. |  |  | VCH/000386/2021-2022 | 224/W | 01/09/2021 | 01/09/2021 | ABHIJIT BERA | 1.3 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Damudarpur W/S Scheme | SM/06884 | Retrofitting | Retrofitting to accomodate for 275 Nos. FHTC connection under JJM in Damudarpur W/S Scheme within Contai - I Dev. Block Block under Tamluk Division, PHE Dte. |  |  | VCH/001043/2020-2021 | 728/W | 18/02/2021 | 18/02/2021 | ABHIJIT BERA | 11.81 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Damudarpur W/S Scheme | SM/06884 | Retrofitting | Retrofitting to accomodate for 275 Nos. FHTC connection under JJM in Damudarpur W/S Scheme within Contai - I Dev. Block Block under Tamluk Division, PHE Dte. |  |  | VCH/001048/2020-2021 | 801/W | 24/02/2021 | 24/02/2021 | PARIA ENTERPRISE | 11.27 | 0 | 0 | 0
Total | [13 empty] | 71.98 | 0 | 0