## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Kanaidighi W/S Scheme | SM/06886 | Retrofitting | Retrofitting to accommodate FHTC under JJM within Kanaidighi PWSS Block Contai-III in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000036/2020-2021 | 2109/TD | 05/11/2020 | 04/05/2021 | DAS ENTERPRISE | 96.3 | 26.7 | 27.72 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Kanaidighi W/S Scheme | SM/06886 | Retrofitting | Retrofitting to accomodate FHTC under JJM Kanaidighi W/S Scheme within Contai - III Block under Tamluk Division, PHE Dte. |  |  | VCH/000594/2020-2021 | 640/W | 13/01/2021 | 13/01/2021 | DAS ENTERPRISE | 52.63 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM Kanaidighi W/S Scheme | SM/06886 | Retrofitting | Retrofitting to accomodate FHTC under JJM Kanaidighi W/S Scheme within Contai - III Block under Tamluk Division, PHE Dte. |  |  | VCH/001208/2020-2021 | 935/W | 18/03/2021 | 18/03/2021 | DAS ENTERPRISE | 16.93 | 0 | 0 | 0
Total | [13 empty] | 165.87 | 26.7 | 16.1