## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Habichak W/S Scheme | SM/06887 | Retrofitting | Retrofitting to accommodate FHTC under JJM within Habichak PWSS Block Chandipur in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000035/2020-2021 | 2112/TD | 05/11/2020 | 04/05/2021 | TAPAS SANTRA | 96.73 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Habichak W/S Scheme | SM/06887 | Retrofitting | Retrofitting to accomodate FHTC under JJM Habichak W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/000227/2021-2022 | 142/W | 22/07/2021 | 22/07/2021 | TAPAS SANTRA | 1.52 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Habichak W/S Scheme | SM/06887 | Retrofitting | Retrofitting to accomodate FHTC under JJM Habichak W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/000593/2020-2021 | 638/W | 14/01/2021 | 14/01/2021 | TAPAS SANTRA | 48.82 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Habichak W/S Scheme | SM/06887 | Retrofitting | Retrofitting to accomodate FHTC under JJM Habichak W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/001045/2020-2021 | 698/W | 02/02/2021 | 02/02/2021 | TAPAS SANTRA | 46.39 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Habichak W/S Scheme | SM/06887 | Retrofitting | Left out portion for laying distribution system of pipe line and its allied works for Habichak & its adjoining mouzas Water Supply Scheme at Chandipur Block under Tamluk Sub Division of Tamluk Division, P.H.E Dte. Purba Medinipur. |  |  | ORD/000108/2021-2022 | 790/TD | 28/09/2021 | 18/10/2021 | TAPAS SANTRA | 6.59 | 0 | 0 | 0
Total | [13 empty] | 200.05 | 0 | 0