## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kotabar W/S Scheme | SM/06888 | Retrofitting | Retrofitting to accomodate FHTC of Village-Kotbar(CT),J.L. No-18 under JJM in Kotbar PWSS Block - Chandipur in the District of Purba Medinipur. | Assistant Engineer |  | ORD/000107/2020-2021 | 2463/TD | 18/12/2020 | 17/01/2021 | RAJ KUMAR SINGHA | 43.46 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kotabar W/S Scheme | SM/06888 | Retrofitting | Retrofitting to accomodate FHTC of Village-Kulapara,J.L. No-9 under JJM in Kotbar PWSS Block - Chandipur in the District of Purba Medinipur. | Assistant Engineer |  | ORD/000108/2020-2021 | 2464/TD | 18/12/2020 | 12/01/2021 | RAJ KUMAR SINGHA | 22.74 | 0 | 0 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kotabar W/S Scheme | SM/06888 | Retrofitting | Retrofitting to accomodate FHTC of Village-Kotbar(CT) of Kotbar Purba & Paschim Para,J.L. No-18 under JJM in Kotbar PWSS Block - Chandipur in the District of Purba Medinipur. | Assistant Engineer |  | ORD/000109/2020-2021 | 2465/TD | 18/12/2020 | 12/01/2021 | RAJ KUMAR SINGHA | 24.58 | 0 | 0 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kotabar W/S Scheme | SM/06888 | Retrofitting | Retrofitting to accomodate FHTC of Village - Kotbar (CT) of Kotbar Purba and Paschim Para under JJM Kotbar W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/001042/2020-2021 | 726/W | 18/02/2021 | 18/02/2021 | RAJ KUMAR SINGHA | 24.17 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kotabar W/S Scheme | SM/06888 | Retrofitting | Retrofitting to accomodate FHTC of Village - Kulapara under JJM Kotbar W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/000402/2021-2022 | 223/W | 01/09/2021 | 01/09/2021 | RAJ KUMAR SINGHA | 1.16 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kotabar W/S Scheme | SM/06888 | Retrofitting | Retrofitting to accomodate FHTC of Village - Kotbar (CT) under JJM Kotbar W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/000613/2020-2021 | 682/W | 27/01/2021 | 27/01/2021 | RAJ KUMAR SINGHA | 42.23 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kotabar W/S Scheme | SM/06888 | Retrofitting | Retrofitting to accomodate FHTC of Village - Kulapara under JJM Kotbar W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/000589/2020-2021 | 683/W | 27/01/2021 | 27/01/2021 | RAJ KUMAR SINGHA | 21.58 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kotabar W/S Scheme | SM/06888 | Retrofitting | Retrofitting to accomodate FHTC of Village - Kotbar (CT) under JJM Kotbar W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/000383/2021-2022 | 222/W | 01/09/2021 | 01/09/2021 | RAJ KUMAR SINGHA | 1.23 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kotabar W/S Scheme | SM/06888 | Retrofitting | Retrofitting to accomodate FHTC of Village - Kotbar (CT) of Kotbar Purba and Paschim Para under JJM Kotbar W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/000289/2021-2022 | 217/W | 27/08/2021 | 27/08/2021 | RAJ KUMAR SINGHA | 0.41 | 0 | 0 | 0
Total | [13 empty] | 181.57 | 0 | 0