## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Saripur PWSS | SM/06889 | Retrofitting | Retrofitting to accomodate FHTC of Village- Saripur,J.L. No-92 under JJM in Saripur PWSS Block - Chandipur in the District of Purba Medinipur. | Assistant Engineer |  | ORD/000110/2020-2021 | 2466/TD | 18/12/2020 | 12/01/2021 | NARAYAN MANDAL | 27.85 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Saripur PWSS | SM/06889 | Retrofitting | Retrofitting to accomodate FHTC of Village- Damodarpur,J.L. No-93 under JJM in Saripur PWSS Block - Chandipur in the District of Purba Medinipur. | Assistant Engineer |  | ORD/000111/2020-2021 | 2467/TD | 18/12/2020 | 12/01/2021 | NARAYAN MANDAL | 27.46 | 0 | 0 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Saripur PWSS | SM/06889 | Retrofitting | Retrofitting to accommodate FHTC (53 nos) under JJM within Saripur PWSS(Balance Work), Block- Chandipur in the District of Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000222/2021-2022 | 639/TSD | 26/10/2021 | 15/11/2021 | NARAYAN MANDAL | 2.52 | 1.69 | 66.95 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Saripur PWSS | SM/06889 | Retrofitting | Retrofitting to accomodate FHTC of Village - Saripur under JJM Saripur W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/000216/2021-2022 | 123/W | 07/07/2021 | 07/07/2021 | NARAYAN MANDAL | 1.54 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Saripur PWSS | SM/06889 | Retrofitting | Retrofitting to accomodate FHTC of Village - Damudarpur under JJM Saripur W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/000608/2020-2021 | 648/W | 25/01/2021 | 25/01/2021 | NARAYAN MANDAL | 25.46 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Saripur PWSS | SM/06889 | Retrofitting | Retrofitting to accomodate FHTC of Village - Damudarpur under JJM Saripur W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/000217/2021-2022 | 124/W | 07/07/2021 | 07/07/2021 | NARAYAN MANDAL | 2 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Saripur PWSS | SM/06889 | Retrofitting | Retrofitting to accomodate FHTC of Village - Saripur under JJM Saripur W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/000597/2020-2021 | 644/W | 13/01/2021 | 13/01/2021 | NARAYAN MANDAL | 26.31 | 0 | 0 | 0
Total | [13 empty] | 113.14 | 1.69 | 1.49