## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Dakshin Dhalhara PWSS | SM/06890 | Retrofitting | Retrofitting to accomodate FHTC of Village-Hariharpur,J.L. No-43 and Village-Uttar Rautori,J.L No-40 under JJM in Dakshin Dhalhara PWSS Block - Nandakumar in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000103/2020-2021 | 2459/TD | 18/12/2020 | 17/01/2021 | ARABINDA GHOSH | 38.54 | 0.88 | 2.27 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Dakshin Dhalhara PWSS | SM/06890 | Retrofitting | Retrofitting to accomodate FHTC of Village-Alisuli,J.L. No-42 under JJM in Dakshin Dhalhara PWSS Block - Nandakumar in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000101/2020-2021 | 2457/TD | 18/12/2020 | 07/01/2021 | KRISHNENDU SEKHAR DAS | 16.12 | 0.59 | 3.64 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Dakshin Dhalhara PWSS | SM/06890 | Retrofitting | Retrofitting to accomodate FHTC of Village-Bet Kalla,J.L. No-41 and Village-Dakshin Dhalhara,J.L No-39 under JJM in Dakshin Dhalhara PWSS Block - Nandakumar in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000102/2020-2021 | 2458/TD | 18/12/2020 | 17/01/2021 | ARABINDA GHOSH | 33.51 | 1.43 | 4.27 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Dakshin Dhalhara PWSS | SM/06890 | Retrofitting | Retrofitting to accomodate FHTC of Village - Hariharpur under JJM Dakshin Dhalhara W/S Scheme within Conai - II Block under Tamluk Division, PHE Dte. |  |  | VCH/001270/2020-2021 | 1033/W | 30/03/2021 | 30/03/2021 | ARABINDA GHOSH | 14.42 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Dakshin Dhalhara PWSS | SM/06890 | Retrofitting | Retrofitting to accomodate FHTC of Village - Hariharpur under JJM Dakshin Dhalhara W/S Scheme within Conai - II Block under Tamluk Division, PHE Dte. |  |  | VCH/000600/2020-2021 | 641/W | 13/01/2021 | 13/01/2021 | ARABINDA GHOSH | 23.24 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Dakshin Dhalhara PWSS | SM/06890 | Retrofitting | Retrofitting to accomodate FHTC of Village - Betkalla under JJM Dakshin Dhalhara W/S Scheme within Nandakumar Block under Tamluk Division, PHE Dte. |  |  | VCH/000595/2020-2021 | 642/W | 13/01/2021 | 13/01/2021 | ARABINDA GHOSH | 21.06 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Dakshin Dhalhara PWSS | SM/06890 | Retrofitting | Retrofitting to accomodate FHTC of Village - Alisuli under JJM Dakshin Dhalhara W/S Scheme within Nandakumar Block under Tamluk Division, PHE Dte. |  |  | VCH/001253/2020-2021 | 1032/W | 27/03/2021 | 27/03/2021 | KRISHNENDU SEKHAR DAS | 3.44 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Dakshin Dhalhara PWSS | SM/06890 | Retrofitting | Retrofitting to accomodate FHTC of Village - Alisuli under JJM Dakshin Dhalhara W/S Scheme within Nandakumar Block under Tamluk Division, PHE Dte. |  |  | VCH/000607/2020-2021 | 647/W | 25/01/2021 | 25/01/2021 | KRISHNENDU SEKHAR DAS | 12.09 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Dakshin Dhalhara PWSS | SM/06890 | Retrofitting | Retrofitting to accomodate FHTC of Village - Betkalla under JJM Dakshin Dhalhara W/S Scheme within Nandakumar Block under Tamluk Division, PHE Dte. |  |  | VCH/001269/2020-2021 | 1034/W | 30/03/2021 | 30/03/2021 | ARABINDA GHOSH | 11.02 | 0 | 0 | 0
Total | [13 empty] | 173.45 | 2.89 | 1.67