## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gogras Keshab Bar W/S Scheme | SM/06891 | Retrofitting | Retrofitting to accomodate FHTC of Village-Gogras Keshab bar,J.L. No-328 and Village-Gogras Kottaluk,J.L. No-329 under JJM in Gogras Keshab Bar PWSS Block - Panskura - I in the District of Purba Medinipur. | Assistant Engineer |  | ORD/000104/2020-2021 | 2460/TD | 18/12/2020 | 17/01/2021 | TARUN KOLEY | 37.07 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gogras Keshab Bar W/S Scheme | SM/06891 | Retrofitting | Retrofitting to accomodate FHTC of Village-Beraberia,J.L. No-330 under JJM in Gogras Keshab Bar PWSS Block - Panskura - I in the District of Purba Medinipur. | Assistant Engineer |  | ORD/000105/2020-2021 | 2461/TD | 18/12/2020 | 07/01/2021 | TARUN KOLEY | 17.22 | 0 | 0 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gogras Keshab Bar W/S Scheme | SM/06891 | Retrofitting | Retrofitting to accomodate FHTC of Village-Purushottampur,J.L. No-331 under JJM in Gogras Keshab Bar PWSS Block - Panskura - I in the District of Purba Medinipur. | Assistant Engineer |  | ORD/000106/2020-2021 | 2462/TD | 18/12/2020 | 12/01/2021 | TARUN KOLEY | 26.29 | 0 | 0 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gogras Keshab Bar W/S Scheme | SM/06891 | Retrofitting | Retrofitting to accomodate FHTC under JJM Gogras Keshab Bar W/S Scheme within village Gogas Keshab Bar and Gogras Kottaluk Mouza under Tamluk Division, PHE Dte. |  |  | VCH/001027/2020-2021 | 700/W | 02/02/2021 | 02/02/2021 | TARUN KOLEY | 36.85 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gogras Keshab Bar W/S Scheme | SM/06891 | Retrofitting | Retrofitting to accomodate FHTC under JJM Gogras Keshab Bar W/S Scheme within village Purushottampur Mouza under Tamluk Division, PHE Dte. |  |  | VCH/001029/2020-2021 | 702/W | 02/02/2021 | 02/02/2021 | TARUN KOLEY | 25.18 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gogras Keshab Bar W/S Scheme | SM/06891 | Retrofitting | Retrofitting to accomodate FHTC under JJM Gogras Keshab Bar W/S Scheme within village Beraberia Mouza under Tamluk Division, PHE Dte. |  |  | VCH/001028/2020-2021 | 701/W | 02/02/2021 | 02/02/2021 | TARUN KOLEY | 17.09 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gogras Keshab Bar W/S Scheme | SM/06891 | Retrofitting | Survey and data collection through mobile application regarding availability of drinking water, Sanitation facility, Rain water harvesting, greywater management and others parameters in High School, upper Primary School, Primary School, Sisu Siksha Kendra of 25 blocks areas under Tamluk Division PHE Dte within Purba Medinipur District. | Assistant Engineer |  | ORD/000429/2022-2023 | 1618/TD | 20/10/2022 | 09/11/2022 | SUDIP MANNA | 3.67 | 3.52 | 96.07 | 100
Total | [13 empty] | 163.37 | 3.52 | 2.16