## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Jagatpur W/S Scheme | SM/06892 | Retrofitting | Retrofitting to accomodate FHTC under JJM Jagatpur W/S Scheme within Panskura - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001033/2020-2021 | 711/W | 09/02/2021 | 09/02/2021 | ARUP KUMAR DEY | 74.34 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Jagatpur W/S Scheme | SM/06892 | Retrofitting | Retrofitting to accommodate FHTC under JJM within Jagatpur PWSS Block Panskura-I in the District of Purba Medinipur. | Assistant Engineer |  | ORD/000034/2020-2021 | 2111/TD | 05/11/2020 | 04/05/2021 | ARUP KUMAR DEY | 88.18 | 0 | 0 | 100
Total | [13 empty] | 162.52 | 0 | 0