## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Purba Bakulda W/S Scheme | SM/06893 | Retrofitting | Re-laying of D.I./G.I./UPVC pipe line under Purba Bakulda W/S Scheme within Panskura Block damaged due to upgradation of moorum road under Tamluk Division, PHE Dte. |  |  | VCH/000214/2021-2022 | 100/W | 05/07/2021 | 05/07/2021 | BIDHAN MONDAL | 12.56 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Purba Bakulda W/S Scheme | SM/06893 | Retrofitting | Retrofitting to accomodate FHTC under JJM of Purba Bakulda W/S Scheme within Panskura - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000145/2021-2022 | 70/W | 24/06/2021 | 24/06/2021 | BIDHAN MONDAL | 20.84 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Purba Bakulda W/S Scheme | SM/06893 | Retrofitting | Charges of entry of Household data in J.J.M website alongwith Household Addhar Details entry in J.J.M. website under Tamluk Division, PHE Dte. |  |  | VCH/001053/2020-2021 | 816/W | 25/02/2021 | 25/02/2021 | MISHRA ENTERPRISE | 4.85 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Purba Bakulda W/S Scheme | SM/06893 | Retrofitting | Retrofitting to accomodate FHTC under JJM of Purba Bakulda W/S Scheme within Panskura - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001041/2020-2021 | 724/W | 18/02/2021 | 18/02/2021 | BIDHAN MONDAL | 33.98 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Purba Bakulda W/S Scheme | SM/06893 | Retrofitting | Retrofitting to accommodate FHTC under JJM within Purba Bakulda PWSS Block Panskura-I in the District of Purba Medinipur. | Assistant Engineer |  | ORD/000033/2020-2021 | 2110/TD | 05/11/2020 | 04/05/2021 | BIDHAN MONDAL | 72.9 | 0 | 0 | 100
Total | [13 empty] | 145.13 | 0 | 0