## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Sofiabad Piped Water Supply Scheme | SM/07093 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Sofiabad PWSS Block-Contai-II (Deshpran) in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000224/2020-2021 | 2792/TD | 01/02/2021 | 02/04/2021 | RELIABLE CONSTRUCTIONS | 70.61 | 34.76 | 49.23 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Sofiabad Piped Water Supply Scheme | SM/07093 | Retrofitting | Retrofitting to accomodate FHTC under JJM Sofiabad W/S Scheme within Deshapran Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001243/2020-2021 | 993/W | 26/03/2021 | 26/03/2021 | RELIABLE CONSTRUCTIONS | 35.85 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Sofiabad Piped Water Supply Scheme | SM/07093 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000001/2025-2026 | 1308/TD | 13/05/2025 | 13/05/2025 | Resource Division | 0.48 | 0 | 0 | 0
Total | [13 empty] | 106.94 | 34.76 | 32.51