## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Bagmari Piped Water Supply Scheme | SM/07094 | Retrofitting | Functional Household Tap Connection to the 1174 nos. Household of Bagmari W/S Scheme within Patashpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. PART-A [Srirampur(118) Bagmari(116)] | Assistant Engineer | Junior Engineer | ORD/000229/2020-2021 | 2864/TD | 09/02/2021 | 11/03/2021 | SWARUPANANDA DAS | 57.51 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Bagmari Piped Water Supply Scheme | SM/07094 | Retrofitting | Functional Household Tap Connection to the 836 nos. Household of Bagmari W/S Scheme within Patashpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. PART-B [Dwarakapur(115) Rannagarpur(119) Dhusurda(239) Kashimpur(240) Joykrishnapur(114)PART] | Assistant Engineer | Junior Engineer | ORD/000230/2020-2021 | 2865/TD | 09/02/2021 | 11/03/2021 | S.K. MONDAL | 38.92 | 25.89 | 66.53 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Bagmari Piped Water Supply Scheme | SM/07094 | Retrofitting | Retrofitting to accomodate FHTC under JJM Bagmari W/S Scheme within Potashpur - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001219/2020-2021 | 965/W | 22/03/2021 | 22/03/2021 | SWARUPANANDA DAS | 47.13 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Bagmari Piped Water Supply Scheme | SM/07094 | Retrofitting | Retrofitting to accomodate FHTC under JJM Bagmari W/S Scheme under Tamluk Division, PHE Dte. |  |  | VCH/001142/2020-2021 | 1118/W | 30/03/2021 | 30/03/2021 | S.K. MONDAL | 25.94 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Bagmari Piped Water Supply Scheme | SM/07094 | Retrofitting | Retrofitting to accomodate FHTC under JJM Bagmari W/S Scheme within Potashpur - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000429/2021-2022 | 302/W | 05/10/2021 | 05/10/2021 | SWARUPANANDA DAS | 2.87 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Bagmari Piped Water Supply Scheme | SM/07094 | Retrofitting | Retrofitting to accomodate FHTC under JJM Bagmari W/S Scheme within Potashpur - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000371/2021-2022 | BP-2021-22-114 | 05/10/2021 | 05/10/2021 | SWARUPANANDA DAS | 7.5 | 0 | 0 | 0
Total | [13 empty] | 179.86 | 25.89 | 14.4