## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Pratapdighi Piped Water Supply Scheme | SM/07095 | Retrofitting | Functional Household Tap Connection to the 225 nos. Household of Pratapdighi W/S Scheme within Patashpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. PART-C [(Jagati(244 ) part,] | Assistant Engineer | Junior Engineer | ORD/000171/2020-2021 | 2721/TD | 21/01/2021 | 10/02/2021 | M/S. NEW DINDA ENTERPRISE | 10.43 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Pratapdighi Piped Water Supply Scheme | SM/07095 | Retrofitting | Functional Household Tap Connection to the 225 nos. Household of Pratapdighi W/S Scheme within Patashpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. PART-B [(Jagati(244 ) part,] | Assistant Engineer | Junior Engineer | ORD/000172/2020-2021 | 2722/TD | 21/01/2021 | 10/02/2021 | GIRI ENTERPRISE | 10.43 | 0 | 0 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Pratapdighi Piped Water Supply Scheme | SM/07095 | Retrofitting | Functional Household Tap Connection to the 1400 nos. Household of Pratapdighi W/S Scheme within Patashpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. PART-A [Pratap Dighi (245), Mangalpur (249)] | Assistant Engineer | Junior Engineer | ORD/000173/2020-2021 | 2809/TD | 04/02/2021 | 26/03/2021 | GIRI CONSTRUCTION | 64.82 | 0 | 0 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Pratapdighi Piped Water Supply Scheme | SM/07095 | Retrofitting | Retrofitting to accomodate FHTC 1400 Nos. connection under JJM Pratapdighi W/S Scheme within Patashpur - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001237/2020-2021 | 972/W | 25/03/2021 | 25/03/2021 | GIRI CONSTRUCTION | 21.89 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Pratapdighi Piped Water Supply Scheme | SM/07095 | Retrofitting | Retrofitting to accomodate FHTC 1400 Nos. connection under JJM Pratapdighi W/S Scheme within Patashpur - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000283/2021-2022 | 159/W | 02/08/2021 | 02/08/2021 | GIRI CONSTRUCTION | 13.24 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Pratapdighi Piped Water Supply Scheme | SM/07095 | Retrofitting | Retrofitting to accomodate FHTC 225 Nos. connection under JJM Pratapdighi W/S Scheme within Patashpur - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000469/2021-2022 | 315/W | 08/10/2021 | 08/10/2021 | GIRI ENTERPRISE | 0.38 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Pratapdighi Piped Water Supply Scheme | SM/07095 | Retrofitting | Retrofitting to accomodate for 225 Nos. FHTC connection under JJM in Pratapdighi W/S Scheme within Potashpur - II Dev. Block Block under Tamluk Division, PHE Dte. (Part-C) |  |  | VCH/000387/2021-2022 | 225/W | 01/09/2021 | 01/09/2021 | M/S. NEW DINDA ENTERPRISE | 0.63 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Pratapdighi Piped Water Supply Scheme | SM/07095 | Retrofitting | Retrofitting to accomodate FHTC 225 Nos. connection under JJM Pratapdighi W/S Scheme within Patashpur - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001222/2020-2021 | 980/W | 23/03/2021 | 23/03/2021 | GIRI ENTERPRISE | 9.77 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Pratapdighi Piped Water Supply Scheme | SM/07095 | Retrofitting | Retrofitting to accomodate for 225 Nos. FHTC connection under JJM in Pratapdighi W/S Scheme within Potashpur - II Dev. Block Block under Tamluk Division, PHE Dte. (Part-C) |  |  | VCH/001052/2020-2021 | 815/W | 24/02/2021 | 24/02/2021 | M/S. NEW DINDA ENTERPRISE | 9.64 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Pratapdighi Piped Water Supply Scheme | SM/07095 | Retrofitting | Renovation of existing pump house at head works & 2nd tube well site of Pratapdighi W/S Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000193/2022-2023 | 409 / CSD | 12/07/2022 | 11/08/2022 | GIRI CONSTRUCTION | 1.36 | 1.35 | 99.29 | 100
Total | [13 empty] | 142.58 | 1.35 | 0.95