## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Paschim Betya Piped Water Supply Scheme | SM/07096 | Retrofitting | Functional Household Tap Connection to the 190 nos. Household of Paschimbetya W/S Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. PART-A [(Balagerya(77 ) ,Aluan(78) ,Part)] | Assistant Engineer | Junior Engineer | ORD/000170/2020-2021 | 2720/TD | 21/01/2021 | 10/02/2021 | SUBRATA KUMAR BERA | 9 | 1.52 | 16.92 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Paschim Betya Piped Water Supply Scheme | SM/07096 | Retrofitting | Functional Household Tap Connection to the 172 nos. Household of Paschimbetya W/S Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. PART-C [(Bara Rasulpur(635)] | Assistant Engineer | Junior Engineer | ORD/000168/2020-2021 | 2718/TD | 21/01/2021 | 10/02/2021 | SUKOMAL BERA | 8.15 | 1.3 | 16.01 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Paschim Betya Piped Water Supply Scheme | SM/07096 | Retrofitting | Functional Household Tap Connection to the 355 nos. Household of Paschimbetya W/S Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. PART-B [(Aluan(78 ) part,Paschimbatya(79)] | Assistant Engineer | Junior Engineer | ORD/000169/2020-2021 | 2719/TD | 21/01/2021 | 15/02/2021 | MRINAL KANTI PRADHAN | 16.73 | 0.64 | 3.8 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Paschim Betya Piped Water Supply Scheme | SM/07096 | Retrofitting | Functional Household Tap Connection to the 190 Nos. Household of Paschimbetya W/S Scheme within Contai - III Block Tamluk Division, PHE Dte. (PART-A) |  |  | VCH/001194/2020-2021 | 843/W | 08/03/2021 | 08/03/2021 | SUBRATA KUMAR BERA | 7.26 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Paschim Betya Piped Water Supply Scheme | SM/07096 | Retrofitting | Retrofitting to accomodate FHTC 355 Nos. connection under JJM Paschim Betya W/S Scheme within Contai - III Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000471/2021-2022 | 329/W | 08/10/2021 | 08/10/2021 | MRINAL KANTI PRADHAN | 2.08 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Paschim Betya Piped Water Supply Scheme | SM/07096 | Retrofitting | Retrofitting to accomodate FHTC 355 Nos. connection under JJM Paschim Betya W/S Scheme within Contai - III Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001218/2020-2021 | 967/W | 22/03/2021 | 22/03/2021 | MRINAL KANTI PRADHAN | 14.01 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Paschim Betya Piped Water Supply Scheme | SM/07096 | Retrofitting | Retrofitting to accomodate FHTC 172 Nos. connection under JJM Paschim Betya W/S Scheme within Contai - III Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001057/2020-2021 | 823/W | 26/02/2021 | 26/02/2021 | SUKOMAL BERA | 6.61 | 0 | 0 | 0
Total | [13 empty] | 63.85 | 3.46 | 5.42