## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Astichak Piped Water Supply Scheme | SM/07098 | Retrofitting | Retrofitting to accommodate FHTC [181 nos.] under JJM in ASTICHAK PWSS within Egra-II Block under Digha Sub-Diviion of Tamluk Division, Purba Medinipur.(Part-B) Dakshin Choumukh(209, part), Gagana(211, part), Paik Bar(212, part), Dhalgoda (Part, 231) [ PART - 1B ]. |  | Junior Engineer | ORD/000272/2020-2021 | 2925/TD | 22/02/2021 | 14/03/2021 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 8.77 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Astichak Piped Water Supply Scheme | SM/07098 | Retrofitting | Retrofitting to accommodate FHTC [206 nos.] under JJM in ASTICHAK PWSS within Egra-II Block under Digha Sub-Diviion of Tamluk Division, Purba Medinipur.(Part-C),Bamaniabar(228), Narubhunya Chak(229). |  | Junior Engineer | ORD/000166/2020-2021 | 2716/TD | 21/01/2021 | 10/02/2021 | DHANANJOY DAS | 9.99 | 0 | 0 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Astichak Piped Water Supply Scheme | SM/07098 | Retrofitting | Retrofitting to accommodate FHTC [740 nos.] under JJM in ASTICHAK PWSS within Egra-II Block under Digha Sub-Diviion of Tamluk Division, Purba Medinipur.( Part-A), Nalbar(227),Dhalgoda (231) part, .Uttar Padma(233), Kashmali(234), .Kumbha Dharbar(235), |  | Junior Engineer | ORD/000167/2020-2021 | 2717/TD | 21/01/2021 | 25/02/2021 | LOKENATH ENTERPRISES | 35.86 | 0 | 0 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Astichak Piped Water Supply Scheme | SM/07098 | Retrofitting | Retrofitting to accommodate FHTC [206 nos.] under JJM in ASTICHAK PWSS within Egra-II Block under Digha Sub-Diviion of Tamluk Division, Purba Medinipur.(Part-D) Jagannath Karbar(213)(Part) |  | Junior Engineer | ORD/000165/2020-2021 | 2715/TD | 21/01/2021 | 10/02/2021 | ANUPAM CONSTRUCTION | 9.99 | 0 | 0 | 40
5 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Astichak Piped Water Supply Scheme | SM/07098 | Retrofitting | Retrofitting to accomodate FHTC 536 Nos. connection under JJM Astichak W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001234/2020-2021 | 982/W | 25/03/2021 | 25/03/2021 | PALCON | 10.68 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Astichak Piped Water Supply Scheme | SM/07098 | Retrofitting | Retrofitting to accomodate for 206 Nos. FHTC connection under JJM in Astichak W/S Scheme within Egra - II Dev. Block Block under Tamluk Division, PHE Dte. |  |  | VCH/000290/2021-2022 | 209/W | 18/08/2021 | 18/08/2021 | DHANANJOY DAS | 5.2 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Astichak Piped Water Supply Scheme | SM/07098 | Retrofitting | Retrofitting to accomodate for 206 Nos. FHTC connection under JJM in Astichak W/S Scheme within Egra - II Dev. Block Block under Tamluk Division, PHE Dte. |  |  | VCH/000233/2021-2022 | 97/W | 07/07/2021 | 07/07/2021 | DHANANJOY DAS | 4.68 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Astichak Piped Water Supply Scheme | SM/07098 | Retrofitting | Retrofitting to accomodate FHTC (206 Nos.) under JJM of Astichak W/S Scheme within Egra-II Block under Tamluk Division, PHE Dte. (Part-D) |  |  | VCH/000539/2021-2022 | 397/W | 25/11/2021 | 25/11/2021 | ANUPAM CONSTRUCTION | 2.65 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Astichak Piped Water Supply Scheme | SM/07098 | Retrofitting | Retrofitting to accomodate FHTC 740 Nos. connection under JJM Astichak W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000394/2021-2022 | 233/W | 07/09/2021 | 07/09/2021 | LOKENATH ENTERPRISES | 25.14 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Astichak Piped Water Supply Scheme | SM/07098 | Retrofitting | Retrofitting to accomodate FHTC 536 Nos. connection under JJM Astichak W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000232/2021-2022 | 160/W | 30/07/2021 | 30/07/2021 | PALCON | 4.33 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Astichak Piped Water Supply Scheme | SM/07098 | Retrofitting | Retrofitting to accomodate FHTC 740 Nos. connection under JJM Astichak W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001238/2020-2021 | 971/W | 25/03/2021 | 25/03/2021 | LOKENATH ENTERPRISES | 10.64 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Astichak Piped Water Supply Scheme | SM/07098 | Retrofitting | Retrofitting to accommodate FHTC [126 nos.] under JJM in ASTICHAK PWSS within Egra-II Block under Digha Sub-Diviion of Tamluk Division, Purba Medinipur.(Part-B) Dakshin Choumukh(209, part), Gagana(211, part), Paik Bar(212, part), Dhalgoda (Part, 231) [ PART - 2B ]. |  | Junior Engineer | ORD/000271/2020-2021 | 2924/TD | 22/02/2021 | 14/03/2021 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 6.1 | 0 | 0 | 0
13 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Astichak Piped Water Supply Scheme | SM/07098 | Retrofitting | Retrofitting to accommodate FHTC [536 nos.] under JJM in ASTICHAK PWSS within Egra-II Block under Digha Sub-Diviion of Tamluk Division, Purba Medinipur.(Part-E) Jagannath Karbar(213)(Part) |  | Junior Engineer | ORD/000164/2020-2021 | 2714/TD | 21/01/2021 | 20/02/2021 | PALCON | 25.95 | 0.39 | 1.51 | 70
14 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Astichak Piped Water Supply Scheme | SM/07098 | Retrofitting | Laying 150mm. dia. D.I. (K-9) Rising main pipe line in between 1st Tube Well to pump house & O.H.R. to Distribution Main including construction of masonry pillar and Thrust concrete block for Astichak Water supply Scheme under Digha Sub-Division of Tamluk Division, P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000370/2022-2023 | 834/TD | 18/07/2022 | 25/07/2022 | ANUPAM CONSTRUCTION | 3.14 | 0 | 0 | 100
Total | [13 empty] | 163.13 | 0.39 | 0.24