## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Badhia Piped Water Supply Scheme | SM/07102 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Badhia PWSS Block Ramnagar-I in the District of Purba Medinipur. | Assistant Engineer |  | ORD/000126/2020-2021 | 2636/TD | 05/01/2021 | 06/03/2021 | AJIT KUMAR SOM | 96.85 | 21.21 | 21.9 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Badhia Piped Water Supply Scheme | SM/07102 | Retrofitting | Retrofitting to accomodate FHTC under JJM Badhia W/S Scheme within Ramnagar - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001246/2020-2021 | 978/W | 26/03/2021 | 26/03/2021 | AJIT KUMAR SOM | 54.53 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Badhia Piped Water Supply Scheme | SM/07102 | Retrofitting | Retrofitting to accomodate FHTC under JJM Badhia W/S Scheme within Ramnagar - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000392/2021-2022 | 230/W | 07/09/2021 | 07/09/2021 | AJIT KUMAR SOM | 21.1 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Badhia Piped Water Supply Scheme | SM/07102 | Retrofitting | Preparation and submission of Revised Detailed Project Report for Retrofitting to accommodate FHTC under JJM in BADHIA piped water supply Scheme within Ramnagar-I Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte. Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000130/2025-2026 | 144/DSD | 14/05/2025 | 21/05/2025 | ASTER CONSULTANCY | 2.76 | 0 | 0 | 100
Total | [13 empty] | 175.24 | 21.21 | 12.1