## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Ranisai Piped Water Supply Scheme | SM/07104 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Ranisai PWSS Block Ramnagar-I in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000116/2020-2021 | 2480/TD | 21/12/2020 | 19/02/2021 | TARUN KOLEY | 94.35 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Ranisai Piped Water Supply Scheme | SM/07104 | Retrofitting | Retrofitting to accomodate FHTC under JJM of Ranisai W/S Scheme |  |  | VCH/000891/2020-2021 | 828/W | 02/03/2021 | 02/03/2021 | TARUN KOLEY | 4.71 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Ranisai Piped Water Supply Scheme | SM/07104 | Retrofitting | Retrofitting to accomodate FHTC under JJM Ranisai W/S Scheme within Ramnagar - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001034/2020-2021 | 712/W | 09/02/2021 | 09/02/2021 | TARUN KOLEY | 80 | 0 | 0 | 0
Total | [13 empty] | 179.06 | 0 | 0