## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Chandanpur Piped Water Supply Scheme | SM/07105 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chandanpur PWSS Block Ramnagar-I in the District of Purba Medinipur. | Assistant Engineer |  | ORD/000115/2020-2021 | 2481/TD | 21/12/2020 | 19/02/2021 | TAPAS SANTRA | 96.74 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Chandanpur Piped Water Supply Scheme | SM/07105 | Retrofitting | Retrofitting to accomodate FHTC under JJM of Chandanpur W/S Scheme |  |  | VCH/000892/2020-2021 | 827/W | 03/03/2021 | 03/03/2021 | TAPAS SANTRA | 16.22 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Chandanpur Piped Water Supply Scheme | SM/07105 | Retrofitting | Retrofitting to accomodate FHTC under JJM Chandanpur W/S Scheme within Ramnagar - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001036/2020-2021 | 714/W | 09/02/2021 | 09/02/2021 | TAPAS SANTRA | 78 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Chandanpur Piped Water Supply Scheme | SM/07105 | Retrofitting | Preparation and submission of Revised Detailed Project Report for Retrofitting to accommodate FHTC under JJM in CHANDANPUR piped water supply Scheme within Ramnagar-I Block under Digha Sub-Division of Tamluk Division,Purba Medinipur District. |  | Junior Engineer | ORD/000135/2025-2026 | 147/DSD | 14/05/2025 | 21/05/2025 | ASTER CONSULTANCY | 2.66 | 0 | 0 | 0
Total | [13 empty] | 193.61 | 0 | 0