## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Haldia Piped Water Supply Scheme | SM/07106 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Haldia PWSS Block - Ramnagar-I in the District of Purba Medinipur. | Assistant Engineer |  | ORD/000136/2020-2021 | 2662/TD | 11/01/2021 | 12/03/2021 | SANKHA ENTERPRISE | 96.1 | 10.96 | 11.4 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Haldia Piped Water Supply Scheme | SM/07106 | Retrofitting | Retrofitting to accomodate FHTC under JJM Haldia W/S Scheme within Ramnagar - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001240/2020-2021 | 966/W | 25/03/2021 | 25/03/2021 | SANKHA ENTERPRISE | 80 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Haldia Piped Water Supply Scheme | SM/07106 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Haldia PWSS within Ramnagar ¿I Block under Tamluk Division, PHE Dte. |  |  | VCH/001132/2020-2021 | 1113/W | 30/03/2021 | 30/03/2021 | SANKHA ENTERPRISE | 3.98 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Haldia Piped Water Supply Scheme | SM/07106 | Retrofitting | Laying of Distribution pipe line by UPVC pipes with allied works for jointing of Existing line( N.P-55A-55B, N.P-56A-56B, 58A-58B) under Haldia & its adjoining mouzas W/S Scheme within Ramnagar-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer | Junior Engineer | ORD/000975/2023-2024 | 986/DSD | 17/01/2024 | 24/01/2024 | LOKENATH ENTERPRISES | 0.97 | 0.94 | 97.42 | 100
Total | [13 empty] | 181.05 | 11.9 | 6.57