## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mandarmani Piped Water Supply Scheme | SM/07107 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Mandarmani PWSS Block - Ramnagar-II in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000138/2020-2021 | 2688/TD | 20/01/2021 | 21/03/2021 | UNIQUE AGENCY | 60.84 | 60.84 | 99.99 | 100
Total | [13 empty] | 60.84 | 60.84 | 99.99