## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Sankarpur Piped Water Supply Scheme | SM/07108 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Sankarpur PWSS Block - Ramnagar-I in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000124/2020-2021 | 2637/TD | 05/01/2021 | 06/03/2021 | MAITY CONSTRUCTION | 94.92 | 93.09 | 98.07 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Sankarpur Piped Water Supply Scheme | SM/07108 | Retrofitting | Continuation work order for Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Aug. Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters | Junior Engineer | ORD/001331/2023-2024 | 895/TD | 07/03/2024 | 01/01/2025 | MISHRA ENTERPRISE | 9.53 | 0 | 0 | 65
Total | [13 empty] | 104.45 | 93.09 | 89.12