## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kanpur Piped Water Supply Scheme | SM/07109 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Kanpur PWSS Block-Ramnagar-II in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000123/2020-2021 | 2634/TD | 05/01/2021 | 06/03/2021 | BASANTA KUMAR MAITY | 96.58 | 3.47 | 3.59 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kanpur Piped Water Supply Scheme | SM/07109 | Retrofitting | Retrofitting to accomodate FHTC under JJM Kanpur W/S Scheme within Ramnagar - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001037/2020-2021 | 715/W | 09/02/2021 | 09/02/2021 | BASANTA KUMAR MAITY | 59.24 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kanpur Piped Water Supply Scheme | SM/07109 | Retrofitting | Retrofitting to accomodate FHTC under JJM Kanpur W/S Scheme within Ramnagar - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001160/2020-2021 | BP-2021-22-29 | 19/07/2021 | 19/07/2021 | BASANTA KUMAR MAITY | 13.32 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kanpur Piped Water Supply Scheme | SM/07109 | Retrofitting | Retrofitting to accomodate FHTC under JJM Kanpur W/S Scheme within Ramnagar - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001244/2020-2021 | 991/W | 26/03/2021 | 26/03/2021 | BASANTA KUMAR MAITY | 20.5 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kanpur Piped Water Supply Scheme | SM/07109 | Retrofitting | Continuation work order for Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Aug. Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters | Junior Engineer | ORD/001331/2023-2024 | 895/TD | 07/03/2024 | 01/01/2025 | MISHRA ENTERPRISE | 9.53 | 2.67 | 28 | 65
Total | [13 empty] | 199.18 | 6.13 | 3.08