## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-IX | SM/07112 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone -IX Block Panskura-II in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000131/2020-2021 | 2657/TD | 11/01/2021 | 12/03/2021 | BARH CONSTRUCTION | 54.91 | 0.22 | 0.41 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-IX | SM/07112 | Retrofitting | Retrofitting to accomodate FHTC under JJM Surface Water Based W/S Scheme under Zone - IX under Tamluk Division, PHE Dte. |  |  | VCH/001195/2020-2021 | 824/W | 10/03/2021 | 10/03/2021 | BARH CONSTRUCTION | 54 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-IX | SM/07112 | Retrofitting | Retrofitting to accomodate FHTC under JJM Surface Water Based W/S Scheme under Zone - IX under Tamluk Division, PHE Dte. |  |  | VCH/001047/2020-2021 | 1122/W | 30/03/2021 | 30/03/2021 | BARH CONSTRUCTION | 0.69 | 0 | 0 | 0
Total | [13 empty] | 109.6 | 0.22 | 0.2