## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-VI | SM/07115 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone -VI(Balance Work) Block Panskura-II in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000120/2020-2021 | 2633/TD | 05/01/2021 | 06/03/2021 | JAGANNATH MAKAR | 96.81 | 193.59 | 199.96 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-VI | SM/07115 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-II within Panskura - II Block under Tamluk Division, PHE Dte. |  |  | VCH/000231/2021-2022 | 158/W | 30/07/2021 | 30/07/2021 | MAA ANANDAMAYEE | 0.34 | 0 | 0 | 0
Total | [13 empty] | 97.15 | 193.59 | 199.26