## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-X | SM/07117 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone -X(Balance Work) Block Panskura-II in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000117/2020-2021 | 2504/TD | 23/12/2020 | 21/02/2021 | JAYANTA KUMAR MONDAL | 96.37 | 192.59 | 199.85 | 100
Total | [13 empty] | 96.37 | 192.59 | 199.85