## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - 1 Water Supply Scheme | SM/07119 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Gholepukuria PWSS (Zone-I)Block -Nandigram-II in the District of Purba Medinipur. | Assistant Engineer |  | ORD/000118/2020-2021 | 2503/TD | 23/12/2020 | 21/02/2021 | M/S. CHANDI CHARAN MISHRA & CO. | 76.13 | 31.88 | 41.88 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - 1 Water Supply Scheme | SM/07119 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - I W/S Scheme within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001207/2020-2021 | 936/W | 18/03/2021 | 18/03/2021 | M/S. CHANDI CHARAN MISHRA & CO. | 22.35 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - 1 Water Supply Scheme | SM/07119 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - I W/S Scheme within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000464/2021-2022 | 296/W | 07/10/2021 | 07/10/2021 | M/S. CHANDI CHARAN MISHRA & CO. | 21.89 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - 1 Water Supply Scheme | SM/07119 | Retrofitting | Continuation Work Order for Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Augmentation Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters | Junior Engineer | ORD/001160/2023-2024 | 2566/TD | 06/10/2023 | 05/12/2023 | MISHRA ENTERPRISE | 9.53 | 1.64 | 17.21 | 100
Total | [13 empty] | 129.9 | 33.52 | 25.81