## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Tamalda PWSS Block - Egra-I in the District of Purba Medinipur. | SM/07477 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Tamalda PWSS Block -Egra-I in the District of Purba Medinipur. | Assistant Engineer |  | ORD/000235/2020-2021 | 2866/TD | 10/02/2021 | 07/03/2021 | AJIT KUMAR SOM | 44.61 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Tamalda PWSS Block - Egra-I in the District of Purba Medinipur. | SM/07477 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Tamalda Piped Water Supply Scheme |  |  | VCH/001121/2020-2021 |  | 15/03/2021 | 15/03/2021 | AJIT KUMAR SOM | 29.34 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Tamalda PWSS Block - Egra-I in the District of Purba Medinipur. | SM/07477 | Retrofitting | Retrofitting to accomodate FHTC under JJM Tamalda W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000436/2021-2022 | BP-2021-22-149 | 09/11/2021 | 09/11/2021 | AJIT KUMAR SOM | 8.58 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Tamalda PWSS Block - Egra-I in the District of Purba Medinipur. | SM/07477 | Retrofitting | Retrofitting to accomodate FHTC under JJM Tamalda W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001261/2020-2021 | 1089/W | 30/03/2021 | 30/03/2021 | AJIT KUMAR SOM | 29.34 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Tamalda PWSS Block - Egra-I in the District of Purba Medinipur. | SM/07477 | Retrofitting | Laying distribution system of Tamalda & its adjoining moujas Water Supply Scheme to support the ongoing FHTC Connection within Egra-I Dev. Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. | Assistant Engineer |  | ORD/000457/2021-2022 | 1930/TD | 28/02/2022 | 15/03/2022 | SOM CONSTRUCTION | 4.84 | 4.84 | 100 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Tamalda PWSS Block - Egra-I in the District of Purba Medinipur. | SM/07477 | Retrofitting | Preparation and submission of Revised Detailed Project Report for Retrofitting to accommodate FHTC under JJM in TAMALDA piped water supply Scheme within Egra-I Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte. Purba Medinipur District. |  |  | ORD/000132/2025-2026 | 145/DSD | 14/05/2025 | 21/05/2025 | ASTER CONSULTANCY | 2.66 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Tamalda PWSS Block - Egra-I in the District of Purba Medinipur. | SM/07477 | Retrofitting | Functional Household Tap Connection for completion of 100 percent house hold coverage at Tamalda & Sonapada Mouza of Tamalda PWSS, GP-Panchroll, Block - Egra - I under Digha Sub-Division, within Tamluk Division, P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/001217/2023-2024 | 981/TD | 13/03/2024 | 24/02/2025 | SAURAV HAZRA | 3.16 | 0 | 0 | 100
Total | [13 empty] | 122.52 | 4.84 | 3.95