## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Silampur W/S Scheme Under Contai-I Block | SM/07479 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Silampur PWSS Block -Contai-I in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000245/2020-2021 | 2876/TD | 11/02/2021 | 13/03/2021 | BASANTA KUMAR MAITY | 77.79 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Silampur W/S Scheme Under Contai-I Block | SM/07479 | Retrofitting | Retrofitting to accomodate FHTC under JJM Silampur W/S Scheme within Contai - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001260/2020-2021 | 1092/W | 30/03/2021 | 30/03/2021 | BASANTA KUMAR MAITY | 55.45 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Silampur W/S Scheme Under Contai-I Block | SM/07479 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Silampur PWSS within Contai ¿I Block under Tamluk Division, PHE Dte. |  |  | VCH/001131/2020-2021 |  | 17/03/2021 | 17/03/2021 | BASANTA KUMAR MAITY | 55.45 | 0 | 0 | 0
Total | [13 empty] | 188.69 | 0 | 0