## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- I under Nandigram - II dev. Block. (Phase-II) | SM/07480 | Retrofitting | Retrofitting to accommodate FHTC (121 nos) under JJM in Gholepukuria PWSS (Zone-I) (Phase -II) within Gholepukuria JL-134(P) - (Gholepukuria Dakshin Para) Nandigram-II dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur.PART-E | Assistant Engineer |  | ORD/000186/2020-2021 | 2752/TD | 27/01/2021 | 16/02/2021 | PULAK KUMAR SAMANTA | 6.33 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- I under Nandigram - II dev. Block. (Phase-II) | SM/07480 | Retrofitting | Retrofitting to accommodate FHTC (387 nos) under JJM in Gholepukuria PWSS (Zone-I) (Phase -II )_within Rankinipur JL-135(P) - (Rankinipur Uttar) &Gholepukuria JL-134(P) - (Madhya Para) Nandigram-II dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. PART-A | Assistant Engineer |  | ORD/000182/2020-2021 | 2748/TD | 27/01/2021 | 16/02/2021 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 19.48 | 0 | 0 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- I under Nandigram - II dev. Block. (Phase-II) | SM/07480 | Retrofitting | Retrofitting to accommodate FHTC (397 nos) under JJM in Gholepukuria PWSS (Zone-I) (Phase -II) within Rankinipur - (Rankinipur Purba) JL-135(P) &Gholepukuria - (Gholepukuria Purba Uttar Para) JL-134(P) Nandigram-II dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur.PART-B | Assistant Engineer |  | ORD/000183/2020-2021 | 2749/TD | 27/01/2021 | 16/02/2021 | ADHIKARY CONSTRUCTION | 20.1 | 0 | 0 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- I under Nandigram - II dev. Block. (Phase-II) | SM/07480 | Retrofitting | Retrofitting to accommodate FHTC (395 nos) under JJM in Gholepukuria PWSS (Zone-I) (Phase -II) within Rankinipur JL-135(P) - (Rankinipur Dakshin) & Gholepukuria JL-134(P) - (Gholepukuria Uttar Para) Nandigram-II dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur.PART-D | Assistant Engineer |  | ORD/000185/2020-2021 | 2751/TD | 27/01/2021 | 16/02/2021 | ROMEO ENGINEER'S CO-OP SOCIETY LTD. | 20.37 | 0 | 0 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- I under Nandigram - II dev. Block. (Phase-II) | SM/07480 | Retrofitting | Retrofitting to accommodate FHTC (424 nos) under JJM in Gholepukuria PWSS (Zone-I) (Phase -II) within Rankinipur JL-135(P) - (Rankinipur Paschim) & GholepukuriaJL-134(P) - (Gholepukuria Dakshin Paschim Para) Nandigram-II dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. PART-C | Assistant Engineer |  | ORD/000184/2020-2021 | 2750/TD | 27/01/2021 | 16/02/2021 | FARID UDDIN AHMED | 21.27 | 0 | 0 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- I under Nandigram - II dev. Block. (Phase-II) | SM/07480 | Retrofitting | Retrofitting to accomodate FHTC under JJM Gholpukuria - I W/S Scheme under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/001103/2020-2021 | 1101/W | 30/03/2021 | 30/03/2021 | ADHIKARY CONSTRUCTION | 10.54 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- I under Nandigram - II dev. Block. (Phase-II) | SM/07480 | Retrofitting | Retrofitting to accomodate FHTC 387 Nos. connection under JJM Gholpukuria Zone - I W/S Scheme (Phase - II) within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. (Part-A) |  |  | VCH/000191/2021-2022 | BP-2021-22-56 | 13/08/2021 | 13/08/2021 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 8.11 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- I under Nandigram - II dev. Block. (Phase-II) | SM/07480 | Retrofitting | Retrofitting to accomodate FHTC under JJM Gholpukuria - I W/S Scheme under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/001106/2020-2021 | 1114/W | 30/03/2021 | 30/03/2021 | PULAK KUMAR SAMANTA | 5.34 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- I under Nandigram - II dev. Block. (Phase-II) | SM/07480 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - I W/S Scheme within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/001133/2020-2021 | 1100/W | 30/03/2021 | 30/03/2021 | ROMEO ENGINEER'S CO-OP SOCIETY LTD. | 8.89 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- I under Nandigram - II dev. Block. (Phase-II) | SM/07480 | Retrofitting | Retrofitting to accomodate FHTC 121 Nos. connection under JJM Gholpukuria Zone - I W/S Scheme (Phase - II) within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. (Part-E) |  |  | VCH/000130/2021-2022 | BP-2021-22-49 | 29/07/2021 | 29/07/2021 | PULAK KUMAR SAMANTA | 0.97 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- I under Nandigram - II dev. Block. (Phase-II) | SM/07480 | Retrofitting | Retrofitting to accomodate FHTC 397 Nos. connection under JJM Gholpukuria Zone - I W/S Scheme (Phase - II) within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. (Part-B) |  |  | VCH/000354/2021-2022 | BP-2021-22-116 | 05/10/2021 | 05/10/2021 | ADHIKARY CONSTRUCTION | 9.55 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- I under Nandigram - II dev. Block. (Phase-II) | SM/07480 | Retrofitting | Retrofitting to accomodate FHTC under JJM Gholpukuria - I W/S Scheme under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/001104/2020-2021 | 1094/W | 30/03/2021 | 30/03/2021 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 11.1 | 0 | 0 | 0
13 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- I under Nandigram - II dev. Block. (Phase-II) | SM/07480 | Retrofitting | Retrofitting to accomodate FHTC 424 Nos. connection under JJM Gholpukuria Zone - I W/S Scheme (Phase - II) within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. (Part-C) |  |  | VCH/000416/2021-2022 | BP-2021-22-146 | 03/11/2021 | 03/11/2021 | FARID UDDIN AHMED | 16.5 | 0 | 0 | 0
Total | [13 empty] | 158.56 | 0 | 0