## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- II under Nandigram - II dev. Block. (Phase-II) | SM/07482 | Retrofitting | Retrofitting to accommodate FHTC (520 nos) under JJM in Gholepukuria PWSS (Zone-II) (Phase -II) within Baishnab Chak (JL-136) - (Baishnab Chak Uttar Paschim Para, Baishnab Chak Purba Dakshin Para &Gholepukuria [JL134(P)] - (Jaykhali Paschim Para) Nandigram-II dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. ,PART-A | Assistant Engineer |  | ORD/000187/2020-2021 | 2753/TD | 27/01/2021 | 21/02/2021 | ZENITH CONSTRUCTION | 26.93 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- II under Nandigram - II dev. Block. (Phase-II) | SM/07482 | Retrofitting | Retrofitting to accommodate FHTC (480 nos) under JJM in Gholepukuria PWSS (Zone-II) (Phase -II) within Gholepukuria [JL-134(P)] - (Purba Dakshin Para & Madhya Jana Para) Nandigram-II dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur.PART-B | Assistant Engineer |  | ORD/000188/2020-2021 | 2754/TD | 27/01/2021 | 21/02/2021 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 24.38 | 0 | 0 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- II under Nandigram - II dev. Block. (Phase-II) | SM/07482 | Retrofitting | Retrofitting to accomodate FHTC 480 Nos. connection under JJM Gholpukuria Zone - II W/S Scheme (Phase - II) within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. (Part-B) |  |  | VCH/000200/2021-2022 | BP-2021-22-59 | 13/08/2021 | 13/08/2021 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 6.49 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- II under Nandigram - II dev. Block. (Phase-II) | SM/07482 | Retrofitting | Retrofitting to accomodate FHTC under JJM Gholpukuria - II W/S Scheme under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/001107/2020-2021 |  | 12/03/2021 | 12/03/2021 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 17.88 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- II under Nandigram - II dev. Block. (Phase-II) | SM/07482 | Retrofitting | Retrofitting to accomodate FHTC 520 Nos. connection under JJM Gholpukuria Zone - II W/S Scheme (Phase - II) within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. (Part-A) |  |  | VCH/000097/2021-2022 | BP-2021-22-44 | 29/07/2021 | 29/07/2021 | ZENITH CONSTRUCTION | 3.86 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- II under Nandigram - II dev. Block. (Phase-II) | SM/07482 | Retrofitting | Retrofitting to accomodate FHTC under JJM Gholpukuria - II W/S Scheme under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/001105/2020-2021 | 1103/W | 30/03/2021 | 30/03/2021 | ZENITH CONSTRUCTION | 23.02 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Gholepukuria PWSS Zone- II under Nandigram - II dev. Block. (Phase-II) | SM/07482 | Retrofitting | Retrofitting to accomodate FHTC 480 Nos. connection under JJM Gholpukuria Zone - II W/S Scheme (Phase - II) within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. (Part-B) |  |  | VCH/001257/2020-2021 | 1104/W | 30/03/2021 | 30/03/2021 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 17.88 | 0 | 0 | 0
Total | [13 empty] | 120.44 | 0 | 0