## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Guria PWSS under Nandakumar Block. | SM/07483 | Retrofitting | Functional Household Tap connection to the 200 nos Household of Guria W/S scheme within Nandakumar Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District PART- B (Mouza-GuriaJL-45). | Assistant Engineer |  | ORD/000177/2020-2021 | 2743/TD | 27/01/2021 | 16/02/2021 | G. S. CONSTRUCTION | 9.5 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Guria PWSS under Nandakumar Block. | SM/07483 | Retrofitting | Functional Household Tap connection to the 200 nos Household of Guria W/S scheme within Nandakumar Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District PART- A (Mouza-Guria JL-45.) | Assistant Engineer |  | ORD/000176/2020-2021 | 2742/TD | 27/01/2021 | 16/02/2021 | MADAN MOHAN MAITY | 9.51 | 4.07 | 42.76 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Guria PWSS under Nandakumar Block. | SM/07483 | Retrofitting | Functional Household Tap connection to the 200 nos Household of Guria W/S scheme within Nandakumar Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District PART- C (Mouza-Guria JL-45). | Assistant Engineer |  | ORD/000178/2020-2021 | 2744/TD | 27/01/2021 | 16/02/2021 | SUDIP MANNA | 9.5 | 1.78 | 18.69 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Guria PWSS under Nandakumar Block. | SM/07483 | Retrofitting | Functional Household Tap connection to the 531 nos Household of Guria W/S scheme within Nandakumar Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District PART- D (Mouza-Betalbasan & Ghatual (282+249= 531 nos), JL-47 & 50. | Assistant Engineer |  | ORD/000179/2020-2021 | 2745/TD | 27/01/2021 | 21/02/2021 | BHOLANATH DEY | 25.08 | 4.72 | 18.82 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Guria PWSS under Nandakumar Block. | SM/07483 | Retrofitting | Functional Household Tap connection to the 300 nos Household of Guria W/S scheme within Nandakumar Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District PART- F (Mouza-Narayanpur,JL-46). | Assistant Engineer |  | ORD/000181/2020-2021 | 2747/TD | 27/01/2021 | 16/02/2021 | MAA KALI CONSTRUCTION | 14.3 | 2.16 | 15.09 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Guria PWSS under Nandakumar Block. | SM/07483 | Retrofitting | Retrofitting to accomodate FHTC under JJM Guria W/S Scheme under Tamluk Division, PHE Dte. |  |  | VCH/001112/2020-2021 | 1108/W | 30/03/2021 | 30/03/2021 | SK. NUR ISLAM | 6.01 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Guria PWSS under Nandakumar Block. | SM/07483 | Retrofitting | Retrofitting to accomodate FHTC under JJM Guria W/S Scheme under Tamluk Division, PHE Dte. |  |  | VCH/001111/2020-2021 | 1098/W | 30/03/2021 | 30/03/2021 | MAA KALI CONSTRUCTION | 12.11 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Guria PWSS under Nandakumar Block. | SM/07483 | Retrofitting | Functional Household Tap Connection for Guria W/S Scheme within Nandakumar Block Tamluk Division, PHE Dte. |  |  | VCH/001063/2020-2021 | 1106/W | 30/03/2021 | 30/03/2021 | G. S. CONSTRUCTION | 9.28 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Guria PWSS under Nandakumar Block. | SM/07483 | Retrofitting | Retrofitting to accomodate FHTC under JJM Guria W/S Scheme under Tamluk Division, PHE Dte. |  |  | VCH/001110/2020-2021 | 1112/W | 30/03/2021 | 30/03/2021 | SUDIP MANNA | 8.61 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Guria PWSS under Nandakumar Block. | SM/07483 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Guria W/S Scheme within Nandakumar Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001134/2020-2021 |  | 17/03/2021 | 17/03/2021 | MADAN MOHAN MAITY | 7.46 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Guria PWSS under Nandakumar Block. | SM/07483 | Retrofitting | Retrofitting to accomodate FHTC 200 Nos. connection under JJM Guria W/S Scheme within Nandakumar Dev. Block under Tamluk Division, PHE Dte. (Part-A) |  |  | VCH/001259/2020-2021 | 1105/W | 30/03/2021 | 30/03/2021 | MADAN MOHAN MAITY | 7.46 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Guria PWSS under Nandakumar Block. | SM/07483 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Guria W/S Scheme within Nandakumar Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001135/2020-2021 | 1096/W | 30/03/2021 | 30/03/2021 | BHOLANATH DEY | 22.75 | 0 | 0 | 0
13 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Guria PWSS under Nandakumar Block. | SM/07483 | Retrofitting | Functional Household Tap connection to the 140 nos. Household of Guria W/S scheme within Nandakumar Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District PART- E (Mouza-Narayanpur,JL-46). | Assistant Engineer |  | ORD/000180/2020-2021 | 2746/TD | 27/01/2021 | 16/02/2021 | SK. NUR ISLAM | 6.64 | 0.34 | 5.15 | 100
14 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Guria PWSS under Nandakumar Block. | SM/07483 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000207/2023-2024 | 1107/TD | 18/03/2024 | 18/03/2024 | Resource Division | 0.19 | 0 | 0 | 0
Total | [13 empty] | 148.39 | 13.06 | 8.8