## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- I PWSS under Sahid Matangini Block. | SM/07484 | Retrofitting | Retrofitting to accommodate (175) nos FHTC under JJM of Balarampur & Joyrampur village in Alinan Zone-I PWSS Block- Sahid Matangini under Tamluk Sub Division of Tamluk Division, PHE Dte within Purba Medinipur District . | Assistant Engineer |  | ORD/000332/2021-2022 | 1717/TD | 01/02/2022 | 21/02/2022 | MUKHERJEE ENTERPRISE | 10.37 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Alinan Zone- I PWSS under Sahid Matangini Block. | SM/07484 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Alinan Zone-I PWSS Block -Sahid Matangini in the District of Purba Medinipur. | Assistant Engineer |  | ORD/000207/2020-2021 | 2819/TD | 05/02/2021 | 22/03/2021 | TAPAS SANTRA | 97.45 | 96.68 | 99.21 | 100
Total | [13 empty] | 107.82 | 96.68 | 89.67