## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Srirampur PWSS under Tamluk Block. | SM/07653 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Srirampur PWSS (Part-I) Block -Tamluk in the District of Purba Medinipur. | Assistant Engineer |  | ORD/000223/2020-2021 | 2835/TD | 05/02/2021 | 22/03/2021 | ARABINDA GHOSH | 113.61 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Srirampur PWSS under Tamluk Block. | SM/07653 | Retrofitting | Retrofitting to accomodate FHTC under JJM Srirampur W/S Scheme within Tamluk Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001264/2020-2021 | 1079/W | 30/03/2021 | 30/03/2021 | ARABINDA GHOSH | 100.54 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Srirampur PWSS under Tamluk Block. | SM/07653 | Retrofitting | Retrofitting to accomodate FHTC under JJM Srirampur W/S Scheme under Tamluk Division, PHE Dte. |  |  | VCH/001099/2020-2021 |  | 12/03/2021 | 12/03/2021 | ARABINDA GHOSH | 100.73 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Srirampur PWSS under Tamluk Block. | SM/07653 | Retrofitting | Retrofitting to accomodate FHTC under JJM Srirampur W/S Scheme within Tamluk Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000348/2021-2022 | BP-2021-22-117 | 05/10/2021 | 05/10/2021 | ARABINDA GHOSH | 13.82 | 0 | 0 | 0
Total | [13 empty] | 328.7 | 0 | 0