## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kanakpur W/S Scheme Potashpur-I Block | SM/07654 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Kanakpur PWSS Block -Potashpur-I in the District of Purba Medinipur. | Assistant Engineer |  | ORD/000203/2020-2021 | 2801/TD | 04/02/2021 | 21/03/2021 | SRIMANTA KUMAR MAITY | 114.41 | 41.4 | 36.18 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kanakpur W/S Scheme Potashpur-I Block | SM/07654 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Kanakpur Piped Water Supply Scheme |  |  | VCH/001114/2020-2021 | 1085/W | 30/03/2021 | 30/03/2021 | SRIMANTA KUMAR MAITY | 41.89 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Kanakpur W/S Scheme Potashpur-I Block | SM/07654 | Retrofitting | Providing Balance FHTC with allied works of Kanakpur mouzas under Kanakpur water supply scheme of Contai Sub Division under Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer |  | ORD/000456/2022-2023 | 1301/TD | 13/09/2022 | 13/10/2022 | THE GODFATHER TRADING COMPANY | 3.52 | 3.51 | 99.87 | 100
Total | [13 empty] | 159.81 | 44.91 | 28.1