## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Baharchandberya W/S Scheme under Deshapran Block. | SM/07655 | Retrofitting | Retrofitting to accomodate FHTC under JJM Baharchand Berya W/S Scheme under Tamluk Division, PHE Dte. |  |  | VCH/001141/2020-2021 | 1119/W | 30/03/2021 | 30/03/2021 | DIPAK KUMAR BAKLY | 23.16 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Baharchandberya W/S Scheme under Deshapran Block. | SM/07655 | Retrofitting | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Baharchandberya W/S Scheme within Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur (For Normal Land) | Assistant Engineer | Junior Engineer | ORD/000314/2023-2024 | 484/TD | 10/05/2023 | 09/07/2023 | END POINT STRUCTURAL DEPARTMENT | 3.58 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Baharchandberya W/S Scheme under Deshapran Block. | SM/07655 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Baharchandberya PWSS Block -Contai-II (Deshpran) in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000206/2020-2021 | 2802/TD | 04/02/2021 | 21/03/2021 | DIPAK KUMAR BAKLY | 111.16 | 39.05 | 35.13 | 70
Total | [13 empty] | 137.9 | 39.05 | 28.32