## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Lakshya PWSS Block - Mahishadal in the District of Purba Medinipur | SM/07656 | Retrofitting | Retrofitting to accomodate FHTC of Lakshya W/S Scheme within Mahishadal under Tamluk Division, PHE Dte. |  |  | VCH/000129/2021-2022 | BP-2021-22-39 | 23/07/2021 | 23/07/2021 | HARIPADA PATTANAYAK | 60.72 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Lakshya PWSS Block - Mahishadal in the District of Purba Medinipur | SM/07656 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Lakshya PWSS Block- Mahishadal in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000222/2020-2021 | 2844/TD | 08/02/2021 | 19/04/2021 | HARIPADA PATTANAYAK | 160.74 | 138.8 | 86.35 | 100
3 | PURBA MEDINIPUR |  | Central Drilling | Retrofitting to accomodate FHTC under JJM in Lakshya PWSS Block - Mahishadal in the District of Purba Medinipur | SM/07656 | Retrofitting | Providing drilling crew and other allied works for construction of Tube Well (300mm X200mm X 280 Mtrs. Depth) by utilising Departmental Machineries for Lakshya W/S Scheme (T/W-I) , Mahisadal Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000139/2023-2024 | 1392/CDD | 19/09/2023 | 17/02/2025 | MENAKA ENTERPRISE | 21.16 | 0 | 0 | 100
Total | [13 empty] | 242.61 | 138.8 | 57.21