## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur | SM/07657 | Retrofitting | Retrofitting to accommodate FHTC (673 nos) under JJM in Mahammadpur PWSS within Mahammadpur JL No.-185 (Dakshin Mahammadpur) in Nandigram-I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Part-C) [2nd Call] | Assistant Engineer | Junior Engineer | ORD/000273/2020-2021 | 2926/TD | 22/02/2021 | 19/03/2021 | TARUN KOLEY | 31.71 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur | SM/07657 | Retrofitting | Retrofitting to accommodate FHTC (100 nos) under JJM in Mahammadpur PWSS within Khariberia JL No.-183 (Khariberia) in Nandigram-I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000261/2020-2021 | 2877/TD | 11/02/2021 | 03/03/2021 | TAPAN BERA | 4.84 | 0 | 0 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur | SM/07657 | Retrofitting | Retrofitting to accommodate FHTC (102 nos) under JJM in Tajpur PWSS within Tajpur (P) J.L.- 210 (Tajpur Dakshin Pally) in Nandigram-I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Part-H) | Assistant Engineer | Junior Engineer | ORD/000262/2020-2021 | 2878/TD | 11/02/2021 | 03/03/2021 | BUNBA CONSTRUCTION | 4.85 | 0 | 0 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur | SM/07657 | Retrofitting | Retrofitting to accommodate FHTC (590 nos) under JJM in Tajpur PWSS within Bartalya - JL No.-209 (Bartalya) & Chargalya (P) - J.L. - 150 (Chargalya) in Nandigram-I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Part-F) | Assistant Engineer | Junior Engineer | ORD/000213/2020-2021 | 2825/TD | 05/02/2021 | 02/03/2021 | KRISHNENDU SEKHAR DAS | 27.98 | 0 | 0 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur | SM/07657 | Retrofitting | Retrofitting to accommodate FHTC (590 nos) under JJM in Tajpur PWSS within Chargalya (P) - J.L. - 150 (Chargalya) & Tajpur (P) - J.L. - 210 (Tajpur & Tajpur Paschim Pally) in Nandigram-I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Part-G) | Assistant Engineer | Junior Engineer | ORD/000214/2020-2021 | 2826/TD | 05/02/2021 | 02/03/2021 | DEBASIS DAS | 27.75 | 0 | 0 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur | SM/07657 | Retrofitting | Retrofitting to accommodate FHTC (409 nos) under JJM in Tajpur PWSS within Dijam Talya - JL No.-149 (Dijam Talya) in Nandigram-I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Part-D) | Assistant Engineer | Junior Engineer | ORD/000211/2020-2021 | 2823/TD | 05/02/2021 | 25/02/2021 | MRITYUNJOY PARIA | 19.4 | 12.43 | 64.05 | 100
7 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur | SM/07657 | Retrofitting | Retrofitting to accommodate FHTC (429 nos) under JJM in Tajpur PWSS within Bar Jamtalya - JL No.-148 (Bar Jamtalya) & Nandanayak Bar - J.L. - 179 (Nandanayak Bar) in Nandigram-I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Part-E) | Assistant Engineer | Junior Engineer | ORD/000212/2020-2021 | 2824/TD | 05/02/2021 | 25/02/2021 | SK. NUR ISLAM | 20.36 | 8.35 | 41.01 | 100
8 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur | SM/07657 | Retrofitting | Retrofitting to accomodate FHTC under JJM Tajpur W/S Scheme under Tamluk Division, PHE Dte. |  |  | VCH/001097/2020-2021 | 1102/W | 30/03/2021 | 30/03/2021 | SK. NUR ISLAM | 12 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur | SM/07657 | Retrofitting | Retrofitting to accomodate FHTC (673 Nos.) under JJM in Mahammadpur W/S Scheme within Nandigram - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000322/2021-2022 | BP-2021-22-88 | 05/10/2021 | 05/10/2021 | TARUN KOLEY | 32.35 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur | SM/07657 | Retrofitting | Retrofitting to accomodate FHTC under JJM Mahammadpur W/S Scheme under Tamluk Division, PHE Dte. |  |  | VCH/001109/2020-2021 | 1093/W | 30/03/2021 | 30/03/2021 | NARAYAN CHANDRA DAS | 19.15 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur | SM/07657 | Retrofitting | Retrofitting to accomodate FHTC 590 Nos. connection under JJM Tajpur W/S Scheme within Nandigram - I Dev. Block under Tamluk Division, PHE Dte. (Part-F) |  |  | VCH/000349/2021-2022 | BP-2021-22-118 | 05/10/2021 | 05/10/2021 | KRISHNENDU SEKHAR DAS | 13.48 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur | SM/07657 | Retrofitting | Retrofitting to accomodate FHTC under JJM Tajpur W/S Scheme under Tamluk Division, PHE Dte. |  |  | VCH/001098/2020-2021 | 1095/W | 30/03/2021 | 30/03/2021 | KRISHNENDU SEKHAR DAS | 14.5 | 0 | 0 | 0
13 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur | SM/07657 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Tajpur W/S Scheme within Nandigram ¿ I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001136/2020-2021 | 1097/W | 30/03/2021 | 30/03/2021 | DEBASIS DAS | 13.78 | 0 | 0 | 0
14 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur | SM/07657 | Retrofitting | Retrofitting to accomodate FHTC 741 Nos. connection under JJM in Mahammadpur W/S Scheme within Nandigram - I Dev. Block under Tamluk Division, PHE Dte. (Part-B) |  |  | VCH/000253/2021-2022 | BP-2021-22-72 | 04/09/2021 | 04/09/2021 | NARAYAN CHANDRA DAS | 16.12 | 0 | 0 | 0
15 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur | SM/07657 | Retrofitting | Retrofitting to accomodate for 409 Nos. FHTC connection under JJM in Tajpur W/S Scheme within Nandigram - I Dev. Block Block under Tamluk Division, PHE Dte. (Part-D) |  |  | VCH/000255/2021-2022 | BP-2021-22-69 | 04/09/2021 | 04/09/2021 | MRITYUNJOY PARIA | 6.98 | 0 | 0 | 0
16 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur | SM/07657 | Retrofitting | Retrofitting to accomodate FHTC for Tajpur W/S Scheme |  |  | VCH/000201/2021-2022 | BP-2021-22-62 | 13/08/2021 | 13/08/2021 | BUMBA CONSTRUCTION | 4.84 | 0 | 0 | 0
17 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur | SM/07657 | Retrofitting | Retrofitting of accommodate FHTC 100 Nos. under JJM in Mahammadpur W/S Scheme within Nandigram - I Block. |  |  | VCH/000192/2021-2022 | BP-2021-22-60 | 13/08/2021 | 13/08/2021 | TAPAN BERA | 4.84 | 0 | 0 | 0
18 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur | SM/07657 | Retrofitting | Laying Left Out UPVC pipe line of Mouza- Di-jamtalya for Tajpur & its adjoinin Mouzas Water Supply Scheme within Nandigram - I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000527/2021-2022 | 1944/TD | 03/03/2022 | 18/03/2022 | MRITYUNJOY PARIA | 4.85 | 4.64 | 95.84 | 100
19 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur | SM/07657 | Retrofitting | Construction of Approach Road for Mahammadpur PWSS RCC Elevated Reservoir of Capacity 350 Cum. Within Nandigram-I Block under Haldia Sub-Division of Tamluk Division., P.H.E. Dte.Length = 150.00 Mtr Width = 3.0 Mtr. Thickness = 150 mm | Assistant Engineer |  | ORD/001214/2023-2024 | 983/TD | 13/03/2024 | 22/04/2024 | SATYABRATA BHAUMIK | 5.74 | 5.74 | 99.98 | 100
20 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur | SM/07657 | Retrofitting | Sinking of 1(one) nos. 100 mm X 50 mm dia. X 280.0 m(av.) depth, Tube well with PVC Pipes including cost of all materials near Sahid Bedi Ashwini Mal house S/O of Bhupendranath Pal Dag No.3261 & 3262 JL No.241 Mouza Gokulnagar at Gokulnagar Gram Panchayat within Nandigram-I Dev. Block under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000478/2024-2025 | 1250/HSD, | 16/12/2024 | 26/12/2024 | S.D. CONSTRUCTION | 2.79 | 0 | 0 | 100
21 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur PWSS & Tajpur PWSS Block - Nandigram-I in the District of Purba Medinipur | SM/07657 | Retrofitting | Earth filling at Boosting Tubewell site of Tajpur PWSS within Nandigram-I Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000409/2024-2025 | 1071/HSD, | 05/11/2024 | 15/11/2024 | M/S SOURAV MAHAPATRA | 2.46 | 0 | 0 | 100
Total | [13 empty] | 290.78 | 31.16 | 10.72