## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur W/S Scheme under Bhagwanpur - I Block | SM/07658 | Retrofitting | Retrofitting to accommodate FHTC (741 nos) under JJM in Mahammadpur PWSS within Mahammadpur JL No.-185- (Uttar Mahammadpur) in Nandigram-I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000210/2020-2021 | 2822/TD | 05/02/2021 | 07/03/2021 | NARAYAN CHANDRA DAS | 35.29 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur W/S Scheme under Bhagwanpur - I Block | SM/07658 | Retrofitting | Functional Household Tap Connection to the 370 nos. Household of Mahammadpur W/S Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. [Mouza-Benauda (16) - Part,Mabarakpur (20)] Part-E. | Assistant Engineer | Junior Engineer | ORD/000024/2021-2022 | 112/TD | 17/05/2021 | 06/06/2021 | SUBHENDU HAZRA | 17.49 | 15.92 | 91 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur W/S Scheme under Bhagwanpur - I Block | SM/07658 | Retrofitting | Functional Household Tap Connection to the 411 nos. Household of Mahammadpur W/S Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. [Mouza-Chapal Ghata (13) - Part, Parial Chak (15),Benauda (16) - Part] Part-D. | Assistant Engineer | Junior Engineer | ORD/000023/2021-2022 | 111/TD | 17/05/2021 | 06/06/2021 | M/S. NEW DINDA ENTERPRISE | 19.33 | 18.1 | 93.64 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur W/S Scheme under Bhagwanpur - I Block | SM/07658 | Retrofitting | Functional Household Tap Connection to the 588 nos. Household of Mahammadpur W/S Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. [Mouza-Mahammadpur (07) - Part, Durbba Chakri (14),Manoharpur (10) - Part] Part-B. | Assistant Engineer | Junior Engineer | ORD/000016/2021-2022 | 109/TD | 17/05/2021 | 11/06/2021 | JASODA ENTERPRISE | 27.79 | 27.79 | 100 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur W/S Scheme under Bhagwanpur - I Block | SM/07658 | Retrofitting | Functional Household Tap Connection to the 1783 nos. Household of Mahammadpur W/S Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District.[Mouza-Mahammadpur(07) - Part] Part-A. | Assistant Engineer | Junior Engineer | ORD/000015/2021-2022 | 108/TD | 17/05/2021 | 16/07/2021 | DAS CONSTRUCTION | 83.89 | 82.45 | 98.29 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Mahammadpur W/S Scheme under Bhagwanpur - I Block | SM/07658 | Retrofitting | Functional Household Tap Connection to the 510 nos. Household of Mahammadpur W/S Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. [Mouza-Manoharpur (10) - Part, Tiraipur (11),Chapal Ghata (13) - Part] Part-C. | Assistant Engineer | Junior Engineer | ORD/000017/2021-2022 | 110/TD | 17/05/2021 | 11/06/2021 | MRINAL KANTI PRADHAN | 24.1 | 20.98 | 87.03 | 100
Total | [13 empty] | 207.9 | 165.25 | 79.48