## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Keshabpur Jalpai PWSS Block - Mahishadal in the District of Purba Medinipur. | SM/07659 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Keshabpur Jalpai PWSS Block - Mahishadal in the District of Purba Medinipur. | Assistant Engineer |  | ORD/000225/2020-2021 | 2843/TD | 08/02/2021 | 19/04/2021 | RAJ KUMAR SINGHA | 222.76 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Keshabpur Jalpai PWSS Block - Mahishadal in the District of Purba Medinipur. | SM/07659 | Retrofitting | Retrofitting to accomodate FHTC under JJM Keshabpur Jalpai W/S Scheme within Mahishadal Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000107/2021-2022 |  | 23/06/2021 | 23/06/2021 | RAJ KUMAR SINGHA | 116.52 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Keshabpur Jalpai PWSS Block - Mahishadal in the District of Purba Medinipur. | SM/07659 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Keshabpur Jalpai W/S Scheme within Mahishadal Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001137/2020-2021 | 1090/W | 30/03/2021 | 30/03/2021 | RAJ KUMAR SINGHA | 28.06 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Keshabpur Jalpai PWSS Block - Mahishadal in the District of Purba Medinipur. | SM/07659 | Retrofitting | Retrofitting to accomodate FHTC under JJM Keshabpur Jalpai W/S Scheme within Mahishadal Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000240/2021-2022 | BP-2021-22-34 | 23/07/2021 | 23/07/2021 | RAJ KUMAR SINGHA | 116.52 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Keshabpur Jalpai PWSS Block - Mahishadal in the District of Purba Medinipur. | SM/07659 | Retrofitting | Retrofitting to accomodate FHTC under JJM Keshabpur Jalpai W/S Scheme within Mahishadal Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000310/2021-2022 |  | 16/09/2021 | 16/09/2021 | RAJ KUMAR SINGHA | 78.17 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to accomodate FHTC under JJM in Keshabpur Jalpai PWSS Block - Mahishadal in the District of Purba Medinipur. | SM/07659 | Retrofitting | Retrofitting to accomodate FHTC under JJM Keshabpur Jalpai W/S Scheme within Mahishadal Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000423/2021-2022 | BP-2021-22-105 | 05/10/2021 | 05/10/2021 | RAJ KUMAR SINGHA | 78.17 | 0 | 0 | 0
Total | [13 empty] | 640.2 | 0 | 0